**Financial Schedule**

**Expected Deliverables, Timeframe and Budget**

Reports should be submitted in English (Times New Roman, Font 12, 30 pages maximum, excluding annexes).

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **#** | **Deliverable** | **Timeframe** | **Duty-Station** | **Budget** | **Amount USD** |
| 1. | Phase I: Inception report | 1 month | Sana’a, Yemen | 15% |  |
| 2. | Phase II: Draft report | 3.5 months | Sana’a, Yemen | 35% |  |
| 3. | Phase III: Final report | 1.5 month | Sana’a, Yemen | 50% |  |
| Total | | 6 months | Total | 100% |  |