CALL FOR PROPOSALS

Ref. No.: CFP-HBTIQ-20-004

Pilot Manufacturing and Operating Mobile Handwashing Trailers 
in the Cities of Baghdad, Mosul, Ramadi, Heet and Yathrib

Purpose of CFP: Support the reduction of COVID-19 transmission risks through hand washing and awareness-raising, particularly in congested public areas, such as markets places, and overcrowded and underserviced urban areas with poor access to clean water.

Submission Start Date: 07 May 2020

Submission Deadline Date and time: 21 May 2020, at 3 pm Baghdad Time

Key Project Information

UN-Habitat Project title: 	Rapid Response to COVID-19 in Iraq through Mobile Handwashing Trailers

Locations: Town/City: 	Baghdad, Mosul (Nineveh), Ramadi and Heet (Anbar) and Yathrib (Salah al Din)

Country: 	Iraq

Anticipated start date: 	04 June 2020

Estimated duration of project in calendar months: 	03 Months

Maximum proposed value in US$ (UN-Habitat Contribution): 	US$ 84,700

Lead Organisation Unit: 	UN-Habitat-Iraq

- Brief Background of the Project

In just 12 weeks, the outbreak of a novel coronavirus disease (COVID-19) has gone from an initially discrete outbreak to a raging pandemic. Statistics show that once the infection has entered the community transmission phase, it can double in scale every 3 to 5 days. Iraq has acted decisively to suppress the transmission of COVID-19 through restrictions of movement, closure of market places, forbidding public gatherings, quarantines, and even the isolation of neighbourhoods. Aside from physical distancing, handwashing is recognised as the simplest yet most effective way to prevent the transmission of the virus, especially among those living in poor and/or conflict affected urban areas.

During the course of the regular assessments that UN-Habitat undertakes in its project locations, its teams have identified several underserviced urban areas where access to clean water represents a daily challenge for residents as well as people shopping, taking public transport and using key public facilities, such as clinics and schools. WHO recommends that during the pandemic hand hygiene stations should be placed in front of the entrance of every public building and transport locations to allow everyone to practice hand hygiene.  The project is relevant to SDG 6, that seeks to “ensure availability and sustainable management of water and sanitation for all”, as a foundation for development towards health, equity, gender equality and education.

This pilot initiative is complementary to current post-conflict urban recovery projects that UN-Habitat is conducting in the cities of Mosul, Heet and Yathrib, and the recent urban upgrading works that it has conducted in Mosul, Ramadi, and Basra.

This proposal aims to pilot the manufacturing and deployment of seven (7) mobile hand-washing stations in cities where UN-Habitat has a well-established field presence and already works in close partnership with the local authorities. These are: Baghdad, Mosul, Ramadi, Heet and the rural town of Yathrib. The deployment of the hand-washing stations, combined with the delivery of basic hygiene awareness, will reduce the risks of contagion in crowded public spaces – such as market places and transportation hubs – and underserviced settlements. The locations will be identified in close coordination with the respective municipalities.

Well aware of the urgency of the situation, UN-Habitat Iraq’s engineering team has designed and drafted the specifications for the manufacturing of the mobile handwashing station. Its field teams will work in close coordination with the selected Implementing Partner and the sector municipal staff of the mentioned cities (where UN-Habitat already has on-going projects and field presence) to identify the best locations for the deployment of the mobile handwashing stations and, in coordination with UNICEF and WHO, train the community workers who will operate the units on a daily basis and provide health advice to people.

The mobile stations consist of locally-produced trailers mounted by a steel and sandwich panel structure that once opened offers a row of taps and basins on the sides of a potable water tank in zinc. The sides of structure (both open and closed) displays clear public health messaging to be partially sponsored by the public or private sector (e.g. a well-established soap/hand sanitizer brand). A lower tank, located beneath the basins, collects the waste water and can be discharged through a tap.

Each station is designed to be operated on a daily basis by a trained community worker in charge of providing essential Health & Hygiene advice to the targeted communities, as well as operating the trailers on a daily basis for 6 days a week for at least 2,5 months (i.e. driving, parking, cleaning, maintaining, refilling the potable water tank and discharging the waste water tank).

At the end of the project, the stations are to be donated to a local NGOs or the municipalities themselves.

- Main activities and outputs

The Implementing Partner (NGO) will be undertaking the following key activities (but not limited to):

Output 1: Mobile and easy-to-operate handwashing station manufactured and deployed in WASH “hot-spots” in 5 target cities.

Activities:

- Identify and hire local skilled and well-reputed manufacturers in the target city able to produce the mobile trailers, as per design.

- Identify a local or international detergent company interested to become a project partner and partially sponsor the initiative, by providing the liquid soap necessary for 10-week operations, in exchange for a high local and international visibility offered by the initiative (reflected in BOQ #2).

- Develop high quality graphics for customised adhesive decals (stickers) that will be applied on the outside and inside of the trailer to promote health messaging and partner brand. All signage and branding are to be pre-approved by UN-Habitat.

- Test and deploy the trailers in locations identified in close coordination with respective municipalities and UN-Habitat teams (5 days per week).

Output 2: Health & hygiene advice provided to citizens in the WASH “hot-spots” in addition to the display of public messaging

Activities:

- Identify, hire, and train community health workers in each target city to drive/operate the mobile handwashing station on a daily basis (5-6 days a week) and deliver while on site COVID-19 awareness raising messaging to community members. The community workers will wear a branded T-shirt and cap with logos of UN-Habitat, Implementing Partner and detergent company.

- Monitor daily usage, receive feedback from citizens and change locations where needed.

- Send brief reports/photos recording public usage on a daily basis (including GPS location mapping).

Output 3: Communications material developed for social media

Activities:

- Provide photos and short video clips (from smartphone) on a daily basis to show usage of the handwashing station and activity, for social media purposes.

- Risk Analysis

- The project locations are relatively stable from a security point of view. Despite this, there is a need for continued vigilance in terms of operational security and implementation. It is essential to possess a good knowledge of all the areas and to establish good contact with local authorities and communities to reduce risks.

- Work in public areas will expose personnel to the risk of infection by COVID-19 and will be therefore equipped with approved Personal Protection Equipment (PPE) to be renewed/washed on a regular basis (gloves, masks and disinfectant gel).

- Although COVID-19 activities are strongly supported by the local authorities, not all community members necessarily embrace health prevention messaging. The Implementing Partner should make all possible efforts to maintain a good rapport with citizens and avoid confrontation and/or instances of vandalism targeting the mobile handwashing stations. Any such incidents should be immediately reported to the Municipality and the Police.

- Eligibility Criteria

| Criteria | Submission Details/ Documents Required |
| --- | --- |
| Legal Status | - Certificate of registration/incorporation i.e., - Proof of registration in Country of Origin. - Proof of registration of Country of Operation - Proof of country operational presence |
| Organization profile and details | - Clear organization profile and structure of the organization indicating: - Organization’s vision, mission and objectives - Management structure - Members of the Governing Board and their Designations, duly certified by the Corporate Secretary, or its equivalent document - Proof of membership to professional associations if any. |
| Financial Capacity | - Audited organization financial statements (balance sheet and income statement) and auditors report for the last two (2) years |
| Exclusive bank account | - Please note that prospective applicant organizations will not be required to open or maintain a separate bank account for the funds provided by UN-Habitat for this project. Only bank account with the name of the applicant organization is required. |
| Integrity and Governance | - The organization should complete and submit a signed Partner Declaration Form - Provide the profiles of the Chairperson of the Board of Directors, Head of the Organization and Chief of Finance |

- Selection Criteria

| Criteria | Submission Details/ Documents Required |
| --- | --- |
| 1. Technical capacity |  |
| 1.1 Does the organization have the relevant experience and proven track record in implementing activities in the areas of the project? Has it managed in the past projects of similar technical complexities and financial size? Is the project linked with the core business of the IP? | - List of WASH interventions and health-related training projects executed in the last 5 years (value, location, donors, nature of projects, execution stage – completed or ongoing). - Demonstrate how the experiences in past projects are relevant in the execution of the current proposal – especially outside IDP camps - References from past donors |
| 1.2 Does the organization have qualified technical staff with the experience and the technical skills required by the project? What is the staff size, type, qualification and education background? | - CVs of key management staff, technical and non-technical staff that will be involved on the project - How many technical staff and health specialists do you have in the concerned Country for implementing the project? Is there reasonable assurance that such technical staff and health specialists required by the project will continue to be available as needed in the Project? |
| 1.3 Does the organization have a clear and strong link with an identifiable constituency relevant to the targeted population of the project? Does it have the ability to impact on the targeted population and on the issues? Does it have strong presence in the field and for how long? Does it have adequate capacity to work in key areas/regions where the proposed field activities will be implemented? | - Demonstrate, describe and provide proof of local operational presence, including link and ability to impact the targeted population. |
| 1.4 Does the organization possess adequate physical facilities, office equipment, transport, etc. to implement the activities? | - Provide location and list of office facilities, vehicles and office equipment locally available to implement the project. |
| 1.5 Does the organization have formal procedures to monitor project execution (e.g. milestones, outputs, expenditures…) | - Provide formal project monitoring policies and procedures |
| 2. Financial and administrative capacity |  |
| 2.1 Has the organization been in operation over a period of at least 2 years to demonstrate its financial sustainability and relevance? | - State the years of operation - Financial statements for the last 2 years |
| 2.2 Does the organization have qualified staff in Finance? Is the current accounting system computerized and does have the capacity to collect and provide separate financial reports on the activities executed under the Agreement of Cooperation? Does it have systems and practices to monitor and report whether the project deliverables and expenditures are within agreed time and budget? Does it have minimum segregation of duties in place (separation between project management, finance/accounting and executive office) | - CVs of key finance and accounting staff - Description and key features and controls of the accounting system used - Organization structure/ Organogram |
| 2.3 Does the organization have the capacity to procure goods and services on a transparent and competitive basis? (if applicable) check for procurement unit with experienced staff | - Copies of procurement policies and procedures. The procedures should show how you procure locally and internationally. |
| 2.4 Does the organization have formal procedures and controls to mitigate fraud such as multiple signature signatories on bank accounts, reporting and prosecution of incidences of fraud? | - Describe anti-fraud controls and provide formal procedures |
| 2.5 Does the organization have capacity to provide in-kind, financial, personnel contribution as UN-Habitat Implementing Partner in this present project? Please give details of contribution nature and size. | - Describe nature and value of contribution (in-kind or cash) |

| 3. Financial Proposal |  |
| --- | --- |
| 3.1 Is the budget for each component of the activity to be performed by the Implementing Partner (i) cost-effective (i.e. the cost should be economical and prudently estimated to avoid any under/over estimation) (ii) justifiable/well supported and (iii) accurate and complete | Budget Proposal <template provided> - BOQ (if applicable) - Other supporting documents |
| 4. Technical Proposal |  |
| 4.1 The technical proposal is sound and responds adequately to the specifications and requirements? | Technical Proposal document <template provided> |
| Cumulative score for ratios |  |

- Notes:

- Interested Organizations must provide information indicating that they are qualified to perform the services (brochure, description of similar assignments, experience in similar conditions, availability of appropriate skills among staff, etc).

- The CFP and accompanying documents must be received in accordance with instructions provided. CFP submitted to a different email address will not be considered.

- CFP from applicants failing to provide the complete information to fulfil the basic eligibility criteria will be considered non-responsive.

- CFP received after the above deadline will not be considered

- Organizations will be selected in accordance with the procedure set out in the UN-Habitat IP Management policy and Standard Operating Procedures.

- CFP from applicants failing to provide the requested information will be disregarded.

- This CFP does not entail any commitment on the part of UN-Habitat, either financial or otherwise. UN-Habitat reserves the right to accept or reject any or all proposals without incurring any obligation to inform the affected applicant(s) of the grounds.

- Important: The BOQ covers only the supply of the required materials needed during the construction. The Implementing Partner will insert their value under the contractual services item in the budget table. The components required for the actual implementation of the activities (i.e work manpower, training, supervision, equipment, logistics, messaging, visibility etc) are to be separated and inserted inside the related fields of the same table.

- All prices must be in USD

UNICEF (2020). COVID-19 Emergency Response – UNICEF Hygiene Programming Guidance Note. 10 March 2020.

UN-Habitat (2020). Key messages – COVID in Informal Settlements