To:     To Whom It May Concern.

Date:  15/01/2021

Attn:

Fax:

From:  UNDP Bosnia and Herzegovina

Subject: Notice on Amendment of BiH/RFP/001/2021 Provision of Services: Final Evaluation of a United Nations (UN) Joint Programme

Dear Sir/Madam,

UNDP BiH made a decision to amend the RfP documentation related to the following:

- Maximum expected duration of contract: until 15 June 2021

- Expected duration of assignment is up to 140 days

- Anticipated due dates for deliverables have been amended as follows:

Task 2: March 2021

Task 3: April 2021

Task 4: first half of May 2021

Task 5: second half of May 2021

Task 6: first half of June 2021

With this notice on amendment, we are also attaching the amended RfP

UNDP BiH uses this opportunity to apologize for any inconvenience that this amendment might have caused.

Best regards,

UNDP BIH