## Sheet1
ANNEX 2 to the Terms of Reference - LIST OF ACTIVITIES
Activity Description | Estimate time of Implementation | Offline/Online | Location | Qty Participant (Person)/activity | Frequency (times) | Required Support | Remark
SOP of Grievance Mechanism | 2021-04-01 | Online | Online conference | 1 | 5 | Expert Fee | 1 (one) expert will support the selected vendor team in developing SOP (max 5 days engagement of expert)
Development of PocketBook Manual (For Village Facilitators) | 2021-04-01 | Online and Offline | Online conference and office based | 20 | 2 | Expert fee; Meeting package | Preparatory work and consultations will be done online. Consolidation of materials can be done offline (2 days)
Village Facilitators (23 person) training | Apr-May 21 | Offline | Jakarta | 28 | 1 | Meeting package; per diem; transport; airplane ticket; PCR test, Mask and hand sanitizer
Village Facilitator mobilization | Apr-May 21 | Offline | Site locations | 23 | 2 | Transport, PCR test, Mask and hand sanitizer | This is to mobilize village facilitators to each site locations. Village facilitators are to live in the assigned locations throughout the assignment period.
Free Prior Inform Concern (FPIC) in all villages | Apr-May 21 | Offline | Site locations | 20 | 322 | Meals; Mask and Hand Sanitizer | At least 14 (fourteen) meeting consultation meetings with various community group (20 people) are conducted in each 23 villages (FPIC process).
community mapping and consultations | Apr-May 21 | Offline | Site Location | 20 | 460 | Meals; Mask and Hand Sanitizer | 30 (thirty) times for each 23 villages. Facilitators are to conduct stakeholder mapping collect baseline information, identify potential local operators.
interview of local operators | Apr-May 21 | Offline | Site Location | 15 | 23 | Meals; Mask and Hand Sanitizer | 1 (one) time for each 23 villages
Letter of Assignments for Local Operator | May - June 2021 | Offline | Site Location | 4 | 69 | Meals; Transport, Mask and Hand Sanitizer | 3 (three) times for each 23 villages
RESCO BOARDS structure and BUMDES Establishment | June -Nov 21 | Offline | Site Location | 15 | 345 | Meals; Mask and Hand Sanitizer | At least 12 (twelve) consultation meetings with communities (approximately 15 community members in each meeting) to select RESCO Board members in each 23 villages, and establishment of BUMDES.
RESCO Board Trainings (RESCO Administration, accounting, bookkeeping, marketing strategy, business development, etc.) | Aug-Nov 21 | Offline | Site Location | 10 | 276 | Meals; Mask and Hand Sanitizer | 10 (ten) board members will go through at least 12 (twelve) trainings for Board Management. The trainings will be conducted in all 23 villages.
FGD / Meetings (regular updates, SOP development, business plan development, etc.) | Aug-Nov 21 | Offline | Site Location | 10 | 322 | Meals; Mask and Hand Sanitizer | 10 (ten) board members will have at least 14 (fourteen) meetings/FGD to develop SOP, business plan, and give regular updates on RESCO management. This will be conducted in all 23 villages.
Village regulation for BUMDES establishment and/or RESCO establishment letter (2 letter for village non BUMDES) | Oct - Nov 21 | Offline | Site Location | 10 | 69 | Meals; Mask and Hand Sanitizer | 10 (10) board members and local government representatives will meet at least 3 (three) times to develop village regulations on BUMDES and/or RESCO establishment leters.
Facilitation on Electricity Tariff | Oct 21-Feb 22 | Offline | Site Location | 20 | 276 | Meals; Mask and Hand Sanitizer | At least 20 (twenty) people representing village governments, RESCO board members,and various community groups will have at least 12 (twelve) meetings to discuss electricity tariff
Notarial Deed for RESCO | Nov 21 - Feb 22 | Offline | Site Location | 10 | 69 | Meals; transport; Mask and Hand Sanitizer | Village facilitator and RESCO board members (10 people) will register RESCO for notarial deed. Posisble to have 3 (three) trps to the nearest town that could provide notarial services. Applicable in all 23 villages
Monitoring and Evaluation | Nov 21 -Sept 22 | Offline | Site Location | 23 | 12 | Transport, PCR test, Mask and hand sanitizer