## Gantt Chart
| DETAILED IMPLEMENTATION PLAN | [6 empty] | Period Highlight: |  |  |  | 1 |  |  |  |  | Plan timeline | [6 empty] | Normal actual timeline | [10 empty] | % Actual activity completed beyond plan | [14 empty] | Current date: |  |  |  | 2022-08-18
| Period: 2022 | [22 empty] | % Plan activity Completed | [10 empty] | Actual timeline beyond plan
| Project: Proposed Construction of Vocational Training Unit | [6 empty] | 2022
| ITEMS OF WORK PER PROJECTS | OUTPUT | Plan start | Plan timeline | Actual start | Actual timeline | Date
SITE LOCATION(s) | [6 empty] | Status (%) / No. of Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64
OPSC Camp, Gombe | PRELIMINARIES
Logistics of Materials
Site Mobilization and Work Setting
Site Clearence
Setting out
SUBSTRUCTURE
Excavation and Earth Work
Blinding
Setting of starter columns iron work
Foundation footing/column base casting/curing
Foundation beam form Work
Foundation beam iron Work
Foundation beam casting/striking of forms/curing
Forming/Blockwork to Floor level/block filling
Ground beam form work/striking of forms
Ground beam iron work and Laying BRC Wire Mesh
Casting of ground beam and starter columns/curing
Back filling and laterite compaction
Laying of hardcore, BRC wire mesh and DPM
DPC Mechanical work
DPC formwork/striking of forms
Casting of DPC/curing
SUPER STRUCTURE
Forming/Block work to lintel level
Columns Formwork/striking of forms
Columns iron work
Casting of column/curing
Lintel formwork
Lintel iron work
Casting of lintel/striking of forms/curing
Blockwork forming to roof beam
Roof beam formwork
Roof beam iron work
Casting of roof beam
Roofing
FINISHING WORK
Electrical work: piping, cabling
Mechanical Work: piping
Doors, Windows and Burglars Installation
Plastering
Screeding and Painting
Electrical fittings and installations
Mechanical fittings and installations
External works
Other finishing
Generall Cleaning of the Site
| Outputs | Project closure
| Progress Reporting, | Certificate of Provisional Acceptance,
Final Acceptance of Completed Works