## BoQ Sum
BOQ-RURAL ROAD REHABILITATION- [Rukha Kiri District]
Province: Battambang |  |  | ITB 03-2022-BTB
District: Rukh Kiri |  |  | Date: 10 September 2022
Communes: Mukh Reah, Preak Chik and Basak |  |  | Total Road length (5.05Km)
Item | Description | Unit | Quantity | Total Unit Price US$ | Total Amount US$ | Remarks
I | GENERAL ITEMS
1.1 | Contractor's Establishment, equipment mobilization/demobilization + Site camp facilities + traffic management | Ls | 1
1.2 | Insurance Accident and liability: workmens compensation, liability insurance and third party | Ps | 1 | 500 | 500
1.3 | Safety and Health provisions Safety and Health provision, traffic management and safety barriers, safety gears for all labourers, drinking water, etc | Ls | 1 | 300 | 300
1.4 | Material testing (complete including laboratory test results in lab and in situ as instructed by EIIP engineer) | Ls | 1
1.5 | Supply and install Project signboards as per the specifications and detailed drawing | No | 3
SUB TOTAL-GENERAL ITEM
II | ROAD WORK AND DRAINAGE
BoQ-1 | RURAL ROAD REHABILITATION - MUKH REAH COMMUNE-1.55km+1 culvert
BoQ-2 | RURAL ROAD REHABILITATION - PREAK CHIK COMMUNE-1.2 km
BoQ-3 | RURAL ROAD REHABILITATION - BASAK COMMUNE-2.3km
SUB TOTAL-ROAD WORK AND DRAINAGE
TOTAL
Note: *Minimun Labour wage is US$ 8.5 /WD

## BoQ-01 Mukh Reah
BOQ-RURAL ROAD REHABILITATION- [Mukh Reah Commune]
Province: Battambang |  |  | ITB 03-2022-BTB
District: Rukh Kiri |  |  | Date: 10 September 2022
Communes: Mukh Reah |  |  | Road length (1.55Km)
Road Name: Laterite road in Prey Svay village
Item | Description | Unit | Quantity | Total Unit Price US$ | Total Amount US$ | Remarks
II | ROAD WORK
2 | SITE CLEARANCE WORKS
2.1 | Setting out road alignment
2.2 | Site Clearing and removal of grass, and bushes within the limits of working area (road formation) all vegetation, surface debris, scattered stones. All wasted material shall be disposed to approved dumping areas. The work shall be carried out by manual labour
a | Light bush clearing grass clearing | m2 | 4700
b | Heavy bush clearing | m2 | 1030
2.4 | Remove unsuitable material at a depth exceeding 15 cm from the road carriageway (where is required) as indicated in the road inventory and instructd by the project engineer | m2 | 450
SUB TOTAL-ROAD CLEARING
3 | EARTH WORKS
The work shall include: Supply material, Spreading, levelling, trim, all labour, equipment related to transporting and compaction. Finishing and grading to any cross-falls (camber), or slopes that may be required. Excess and Unsuitable soil must be removed and dumped in authorized sites as instructed by the project engineer.
3.3 | Fill embankment by transported soil. Supply the selected soil, fill, spread, level and compact by roller in layers not exceeding 150 mm, to 95% of maximum dry density, using approved and suitable filling material. Spreading soil for levelling shall be done by labour. | m3 | 2076
3.4 | Filling embankment by excavated soil from surrounding borrow pits (by manual labour). Excavate, haul (no exceeding 50m hauling distance), fill, spread, level and compact by roller in layers not exceeding 150 mm, to 95% of maximum dry density, using approved and suitable filling material. | m3 | 1300
3.5 | Excavate for side drain by manual labour, to be completed as specified in the typical drawing & to the Project Engineer's satisfaction. Excess and unsuitable soil must be removed from excavated side drain of a minimum 1.5m. Excavated soil found suitable for re-use shall be spread and compacted as instructed by project engineer. | m3 | 124
SUB TOTAL-EARTHWORK
4 | ROAD PAVEMENT AND SURFACE
The works Include surfaces preparation, samples, Laboratory tests, compaction, watering. The works shall be executed as Shown in the typical draining and specifications to the satisfaction of the project Engineer. Rate shall include all related equipment, labour, transportation, compaction, finishing etc
4.1 | Gravel wearing course Supply and compact the gravel layer laid on compacted earthwork. The gravel layer shall be spread by labour to the designed level and cross fall(7%) as stated in the typical drawing. Compaction shall be done by roller after the gravel is spread to achieve not less than 100% of maximum dry density at optimum moisture as determined by ASTM D 1556 | m3 | 930
SUB TOTAL-ROAD PAVEMENT
III | DRAINAGE STRUCTURE(CONSTRUCTION OF CONCRETE DRAIN, RETAINING WALL AND CULVERTS)
5.1 | Excavation for foundations by maunal labour Excess and unsuitable soil removed, deposited, or reused at locations authorized by the Project Engineer. Excavated soil found suitable for re-use stored at the appropriate location for backfilling. | m3 | 22.01
5.2 | Backfill around foundations from selective excavated materials, including compaction in layers not exceeding 150mm thickness. Where the soil from the excavation is unusable, selected good soils to be imported. | m3 | 7.49
5.3 | Soil Backfill for Detour, including compaction in layers not exceeding 150mm thickness. Where the soil from the excavation is unusable, selected good soils to be imported. | m3 | 26
5.5 | Supply and construct lean concrete for foundations. The thickness of the lean concrete shall be 10 cm or otherwise as specified in the drawing. The mix proportion for the lean concrete is 1:3:6 (in volume). The concrete should be mixed by using small concrete mixer and cast in situ. | m3 | 1.87
5.6 | Supply and place concrete (price without steel bars) - for headwalls, wing walls, cut off wall and aprons Concrete having a strength of F'c=25 MPa or the mixing proportion is 1:2:4. The work shall include weep holes wherever specified. | m3 | 3.61
5.7 | Supply and construct High Tensile Steel Reinforcement for concrete structures (all diameters). The price shall include, cutting, bending, tying wire, fixing and waste from the cuts - all inclusive. | kg | 97.76
5.8 | Supply and install concrete pipes including installation and sealing of the joints by morta 1:3 (in volume) as specified
| Reinforced concrete pipe diameter 100cm | No
| Reinforced concrete pipe diameter 80 cm | No
| Reinforced concrete pipe diameter 60 cm | No | 6
5.9 | Supply and install formwork: The price includes formwork installed all support, bracing, and other accessories and all inclusive. | m2 | 8.92
SUB TOTAL-ROAD FURNITURE-DRAINAGE STRUCTURE
IV | TURFING
5.11 | Turfing/grass planting: The price shall include, ground preparation, supply the grass, plant and until end of the maintenance period | m2 | 3100
5.12 | Tree planting: The price shall include, ground preparation, supply the tree, plant and until end of the maintenance period | No | 620
SUB TOTAL-TURFING/PLAITING GRASS
TOTAL
Note: *Minimun Labour wage is US$ 8.5 /WD

## BoQ-02 Preak Chik
BOQ-RURAL ROAD REHABILITATION- [Preak Chik commune]
Province: Battambang |  |  | ITB 03-2022-BTB
District: Rukh Kiri |  |  | Date: 10 September 2022
Communes: Preak Chik |  |  | Road length (1.20Km)
Road Name: Laterite road in Preaek Chik village
Item | Description | Unit | Quantity | Total Unit Price US$ | Total Amount US$ | Remarks
II | ROAD WORK
2 | SITE CLEARANCE WORKS
2.1 | Setting out road alignment
2.2 | Site Clearing and removal of grass, and bushes within the limits of working area (road formation) all vegetation, surface debris, scattered stones. All wasted material shall be disposed to approved dumping areas. The work shall be carried out by manual labour
a | Light bush clearing grass clearing | m2 | 2400
b | Heavy bush clearing | m2 | 775
SUB TOTAL-ROAD CLEARING
3 | EARTH WORKS
The work shall include: Supply material, Spreading, levelling, trim, all labour, equipment related to transporting and compaction. Finishing and grading to any cross-falls (camber), or slopes that may be required. Excess and Unsuitable soil must be removed and dumped in authorized sites as instructed by the project engineer.
3.3 | Fill embankment by transported soil. Supply the selected soil, fill, spread, level and compact by roller in layers not exceeding 150 mm, to 95% of maximum dry density, using approved and suitable filling material. Spreading soil for levelling shall be done by labour. | m3 | 638
3.4 | Filling embankment by excavated soil from surrounding borrow pits (by manual labour). Excavate, haul (no exceeding 50m hauling distance), fill, spread, level and compact by roller in layers not exceeding 150 mm, to 95% of maximum dry density, using approved and suitable filling material. | m3 | 350
3.5 | Excavate for side drain by manual labour, to be completed as specified in the typical drawing & to the Project Engineer's satisfaction. Excess and unsuitable soil must be removed from excavated side drain of a minimum 1.5m. Excavated soil found suitable for re-use shall be spread and compacted as instructed by project engineer. | m3 | 110
SUB TOTAL-EARTHWORK
4 | ROAD PAVEMENT AND SURFACE
The works Include surfaces preparation, samples, Laboratory tests, compaction, watering. The works shall be executed as Shown in the typical draining and specifications to the satisfaction of the project Engineer. Rate shall include all related equipment, labour, transportation, compaction, finishing etc
4.1 | Gravel wearing course Supply and compact the gravel layer laid on compacted earthwork. The gravel layer shall be spread by labour to the designed level and cross fall(7%) as stated in the typical drawing. Compaction shall be done by roller after the gravel is spread to achieve not less than 100% of maximum dry density at optimum moisture as determined by ASTM D 1556 | m3 | 870
SUB TOTAL-ROAD PAVEMENT
IV | TURFING
5.11 | Turfing/grass planting: The price shall include, ground preparation, supply the grass, plant and until end of the maintenance period | m2 | 2400
5.12 | Tree planting: The price shall include, ground preparation, supply the tree, plant and until end of the maintenance period | No | 480
SUB TOTAL-TURFING/PLAITING GRASS
TOTAL
Note: *Minimun Labour wage is US$ 8.5 /WD

## BoQ-03 Basak
BOQ-RURAL ROAD REHABILITATION- [Bask Commune]
Province: Battambang |  |  | ITB 03-2022-BTB
District: Rukh Kiri |  |  | Date: 10 September 2022
Communes: Basak |  |  | Road length (2.30Km)
Road Name: Laterite road in Ou Romchek village
Item | Description | Unit | Quantity | Total Unit Price US$ | Total Amount US$ | Remarks
II | ROAD WORK
2 | SITE CLEARANCE WORKS
2.1 | Setting out road alignment
2.2 | Site Clearing and removal of grass, and bushes within the limits of working area (road formation) all vegetation, surface debris, scattered stones. All wasted material shall be disposed to approved dumping areas. The work shall be carried out by manual labour
a | Light bush clearing grass clearing | m2 | 4600
b | Heavy bush clearing | m2 | 2175
SUB TOTAL-ROAD CLEARING
3 | EARTH WORKS
The work shall include: Supply material, Spreading, levelling, trim, all labour, equipment related to transporting and compaction. Finishing and grading to any cross-falls (camber), or slopes that may be required. Excess and Unsuitable soil must be removed and dumped in authorized sites as instructed by the project engineer.
3.3 | Fill embankment by transported soil. Supply the selected soil, fill, spread, level and compact by roller in layers not exceeding 150 mm, to 95% of maximum dry density, using approved and suitable filling material. Spreading soil for levelling shall be done by labour. | m3 | 1191
3.4 | Filling embankment by excavated soil from surrounding borrow pits (by manual labour). Excavate, haul (no exceeding 50m hauling distance), fill, spread, level and compact by roller in layers not exceeding 150 mm, to 95% of maximum dry density, using approved and suitable filling material. | m3 | 500
3.5 | Excavate for side drain by manual labour, to be completed as specified in the typical drawing & to the Project Engineer's satisfaction. Excess and unsuitable soil must be removed from excavated side drain of a minimum 1.5m. Excavated soil found suitable for re-use shall be spread and compacted as instructed by project engineer. | m3 | 1139
SUB TOTAL-EARTHWORK
4 | ROAD PAVEMENT AND SURFACE
The works Include surfaces preparation, samples, Laboratory tests, compaction, watering. The works shall be executed as Shown in the typical draining and specifications to the satisfaction of the project Engineer. Rate shall include all related equipment, labour, transportation, compaction, finishing etc
4.1 | Gravel wearing course Supply and compact the gravel layer laid on compacted earthwork. The gravel layer shall be spread by labour to the designed level and cross fall(7%) as stated in the typical drawing. Compaction shall be done by roller after the gravel is spread to achieve not less than 100% of maximum dry density at optimum moisture as determined by ASTM D 1556 | m3 | 1380
SUB TOTAL-ROAD PAVEMENT
IV | TURFING
5.11 | Turfing/grass planting: The price shall include, ground preparation, supply the grass, plant and until end of the maintenance period | m2 | 4600
5.12 | Tree planting: The price shall include, ground preparation, supply the tree, plant and until end of the maintenance period | No | 920
SUB TOTAL-TURFING/PLAITING GRASS
TOTAL
Note: *Minimun Labour wage is US$ 8.5 /WD

## BoQ-Road work-KH
BOQ-RURAL ROAD REHABILITATION- [ROAD NAME]
ខេត្តៈ
ស្រុកៈ
ឃុំៈ
ឈ្មោះផ្លូវៈ
ល.រ | ការពិពណ៌នា | ឯកតា
I | GENERAL ITEMS ការងារទូទៅ
1.1 | Contractor's Establishment, equipment mobilization/demobilization + Site camp facilities + traffic management ក្រុមហ៊ុនរៀបចំក្រុមការងារ និង ដឹកជញ្ជូនគ្រឿងចក្រទៅការដ្ឋាន ដឹកជញ្ជូនគ្រឿងចក្រពីការដ្ឋាន កន្លែងបោះទីតាំងការដ្ឋាន និង ការគ្រប់គ្រងចរាចរណ៍ | Ls
1.2 | Insurance Accident and liability: workmens compensation, liability insurance and third party ការធានារ៉ាប់រង គ្រោះថ្នាក់ និងទំនួលខុសត្រូវ៖ សំណងកម្មករ ទំនួលខុសត្រូវលើការធានារ៉ាប់រង និងភាគីទីបី | Ps
1.3 | Safety and Health provisions Safety and Health provision, traffic management and safety barriers, safety gears for all labourers, drinking water, etc បទប្បញ្ញត្តិសុវត្ថិភាព និងសុខភាព ការផ្តល់សុវត្ថិភាព និងសុខភាព ការគ្រប់គ្រងចរាចរណ៍ និង របាំងសុវត្ថិភាព ការផ្គត់ផ្គង់ទឹកផឹក កាលផ្តល់នូវឧបករណ៍សុវត្ថិភាពសម្រាប់កម្មករទាំងអស់ ។ល។ | Ls
1.4 | Material testing (complete including laboratory test results in lab and in situ as instructed by EIIP engineer) ការធ្វើតេស្តសម្ភារៈ (លទ្ធផលតេស្តនៅក្នុងមន្ទីរពិសោធន៍ និងនៅកន្លែងដូចដែលណែនាំដោយវិស្វករ EIIP) | Ls
1.5 | Supply and install Project signboards as per the specifications and detailed drawing ការផ្គត់ផ្គង់ និងសាងសង់ស្លាកសញ្ញាគម្រោង ដោយអនុលោមតាមបទដ្ឋានបច្ចេកទេស និងប្លង់បច្ចេកទេស | No
SUB TOTAL-GENERAL ITEM តម្លៃសរុបរង សម្រាប់ការងារទូទៅ
II | ROAD WORK ការងារផ្លូវ
2 | SITE CLEARANCE WORKS ការឈូសឆាយសម្អាតទីតាំង
2.1 | Setting out road alignment ការកំណត់តួផ្លូវ
2.2 | Site Clearing and removal of grass, and bushes within the limits of working area (road formation) all vegetation, surface debris, scattered stones. All wasted material shall be disposed to approved dumping areas. The work shall be carried out by manual labour ការឈូសឆាយសម្អាតទីតាំង និងការសម្អាតស្មៅ
a | Light bush clearing grass clearing ការសម្អាតស្មៅ | m2
b | Heavy bush clearing ការកាប់ឆ្ការគុម្ពព្រៃ | m2
2.3 | Tree cutting and removal of the tree stump. Only the trees within the road carriageway should be removed, other trees shall be kept. -tree dia metter 10cm-15 cm) កាប់ដើមឈើ និងសម្អាតឬសដែលប៉ះពាល់នឹងខ្នងផ្លូវសាងសង់ ដើមឈើនៅតាមជើងផ្លូវគួរតែរក្សារដូចដើម | No
2.4 | Remove unsuitable material at a depth exceeding 15 cm from the road carriageway (where is required) as indicated in the road inventory and instructd by the project engineer ការកាយដីស្អុយ, សំរាម និងឬសឈើស្អុយផ្សេងៗនៅលើខ្នងផ្លូវនឹងសាងសង នៅកំពស់លើសពី១៥សម ជាការតម្រូវពីវិស្វករគម្រោង | m2
SUB TOTAL-ROAD CLEARING ការសម្អាតដីផ្សេងៗ
3 | EARTH WORKS ការងារដី
The work shall include: Supply material, Spreading, levelling, trim, all labour, equipment related to transporting and compaction. Finishing and grading to any cross-falls (camber), or slopes that may be required. Excess and Unsuitable soil must be removed and dumped in authorized sites as instructed by the project engineer. ការងារត្រូវគិតទាំង ការផ្គត់ផ្គង់សម្ភារៈប្រើប្រាស់ផ្សេងៗ សម្រាប់ការពង្រាយដីទៅតាមកំរិតកំពស់ត្រូវការ, ការបង្ហាប់ដី, ជីកកកាយផ្សេងៗ។ ដីដែលត្រូវកាយចោលនឹងដឹកទៅចាក់នៅកន្លែងដែលមានការអនុញ្ញាតត្រឹមត្រូវ តាមការណែនាំរបស់វិស្វករគម្រោង។
3.1 | Excavate by the manual labour of road subgrade, widening road width to be completed as specified in the typical drawing & to the project Engineer's satisfaction. Excavated soil found suitable for re-use shall be spread and compacted as instructed by the project engineer. ការកាយដីដោយប្រើប្រាស់កម្លាំងពលកម្មសម្រាប់ស្រទាប់ក្រោម, ការពង្រីកទទឹងខ្នងផ្លូវតាមបទដ្ឋាន និងតាមការណែនាំរបសវិស្វករគម្រោង។​ ដីដែលអាចប្រើប្រាស់បាននឹងទុកសម្រាប់ប្រើប្រាស់ម្តងទៀត។ | m3
3.2 | Excavate by the equipment of road subgrade, widening road width to be completed as specified in the typical drawing & to the project Engineer's satisfaction. Excavated soil found suitable for re-use shall be spread and compacted as instructed by the project engineer. ការកាយដីដោយប្រើប្រាស់គ្រឿងចក្រសម្រាប់ស្រទាប់ក្រោម, ការពង្រីកទទឹងខ្នងផ្លូវតាមបទដ្ឋាន និងតាមការណែនាំរបសវិស្វករគម្រោង។​ ដីដែលអាចប្រើប្រាស់បាននឹងទុកសម្រាប់ប្រើប្រាស់ម្តងទៀត។ | m3
3.3 | Fill embankment by transported soil. Supply the selected soil, fill, spread, level and compact by roller in layers not exceeding 150 mm, to 95% of maximum dry density, using approved and suitable filling material. Spreading soil for levelling shall be done by labour. ការចាក់បំពេញខ្នងផ្លូវដោយប្រើប្រាស់ដីដែលដឹកពីកន្លែងផ្សេងៗ។ ដីដែលចាក់បំពេញ ពង្រាយ និងបង្ហាប់មិនអោយលើសពីកំពស់១៥០មម ហើយដីត្រូរមានកំហាប់ស្ងួតស្មើរនឹង៩៥%, ដីដែលប្រើប្រាស់ត្រូវទទួលបានការអនុញ្ញាតអោយប្រើប្រាស់។ ការពង្រាយដីគួរតែប្រើប្រាស់កំលាំងពលកម្ម។ | m3
3.4 | Filling embankment by excavated soil from surrounding borrow pits (by manual labour). Excavate, haul (no exceeding 50m hauling distance), fill, spread, level and compact by roller in layers not exceeding 150 mm, to 95% of maximum dry density, using approved and suitable filling material. ការចាក់បំពេញខ្នងផ្លូវដោយប្រើប្រាស់ដីដែលជីកយកពីប្រឡាយក្បែរផ្លូវ។ ដីដែលចាក់បំពេញ ពង្រាយ និងបង្ហាប់មិនអោយលើសពីកំពស់១៥០មម ហើយដីត្រូរមានកំហាប់ស្ងួតស្មើរនឹង៩៥%, ដីដែលប្រើប្រាស់ត្រូវទទួលបានការអនុញ្ញាតអោយប្រើប្រាស់។ | m3
3.5 | Excavate for side drain by manual labour, to be completed as specified in the typical drawing & to the Project Engineer's satisfaction. Excess and unsuitable soil must be removed from excavated side drain of a minimum 1.5m. Excavated soil found suitable for re-use shall be spread and compacted as instructed by project engineer. ការជីក និងកាយប្រឡាយខាងឆ្វេង ឫខាងស្តាំ ដោយកំលាំងពលកម្ម ទៅតាមបទដ្ឋានដែលបានកំណត់។ ដីដែលលើស និងដីស្អុយតម្រូវអោយកាយចេញពីប្រឡាយក្នុងជម្រៅទាបបំផុត១.៥ម។ | m3
SUB TOTAL-EARTHWORK ការងារដីផ្សេងៗ
4 | ROAD PAVEMENT AND SURFACE ខ្នង និងស្រទាប់ផ្លូវ
The works Include surfaces preparation, samples, Laboratory tests, compaction, watering. The works shall be executed as Shown in the typical draining and specifications to the satisfaction of the project Engineer. Rate shall include all related equipment, labour, transportation, compaction, finishing etc ការងារស្រទាប់ផ្លូវ, ដីគម្រូ, ការវាយតំលៃតាមបច្ចេកទេស, ការបង្ហាប់, និងបាញ់ទឹក។ ការងារទាំងនេះនឹងយកតាមបទដ្ឋានដែលបានកំណត់។ តម្លៃនឹងគិតរូមបញ្ជូលទាំងសម្ភារះប្រើប្រាស់, ពលកម្ម, ការដឹងជញ្ជូន, ការបង្ហាប់, និងការងារបញ្ចប់ផ្សេងៗ។
4.1 | Gravel wearing course Supply and compact the gravel layer laid on compacted earthwork. The gravel layer shall be spread by labour to the designed level and cross fall(7%) as stated in the typical drawing. Compaction shall be done by roller after the gravel is spread to achieve not less than 100% of maximum dry density at optimum moisture as determined by ASTM D 1556 ការប្រើប្រាស់ថ្មក្រួស និងបង្ហាប់ពីលើដីដែលបង្ហាប់ហើយ។ ថ្មក្រួសត្រូវតែប្រើប្រាស់កំលាំងពលកម្មសំរាប់ពង្រាយតាមបទដ្ឋានដែលបានណែនាំ។ ការបង្ហាប់ត្រូវប្រើប្រាស់រ៉ូឡូកិនដី។ | m3
SUB TOTAL-ROAD PAVEMENT ការងារក្រាលផ្លូវផ្សេងៗ
III | DRAINAGE STRUCTURE(CONSTRUCTION OF CONCRETE DRAIN, RETAINING WALL AND CULVERTS) សំណង់ទឹកផ្សេងៗ(ប្រឡាយប៉ែតុង, ជញ្ជាំងទប់ដី, និងលូរកាត់ផ្លូវ)។
5.1 | Excavation for foundations by maunal labour Excess and unsuitable soil removed, deposited, or reused at locations authorized by the Project Engineer. Excavated soil found suitable for re-use stored at the appropriate location for backfilling. ការងារជីកដីដោយកំលាំងពលកម្ម។ ដីដែលលើស និងស្អុយត្រូវបានយកចេញ ហើយរក្សារទុកដីដែលអាចប្រើប្រាស់បានដោយមានការត្រួតពិនិត្យពីវិស្វករគម្រោង។ កាយដីដែលអាចប្រើប្រាស់បាន និងរក្សារទុកនៅកន្លែងសមរម្យសម្រាប់ការងារដីបំពេញ។ | m3
5.2 | Backfill around foundations from selective excavated materials, including compaction in layers not exceeding 150mm thickness. Where the soil from the excavation is unusable, selected good soils to be imported. ការងារដីបំពេញគ្រឹះជំវិញ ដោ​យបង្ហាប់មិនអោយកំរាស់លើសពី១៥០មម។ បើដីដែលកាយមិនអាចប្រើប្រាស់បាន ត្រូវប្រើប្រាស់ដីដែលដឹកពីកន្លែងផ្សែងមកជំនួស។ | m3
5.3 | Soil Backfill for Detour, including compaction in layers not exceeding 150mm thickness. Where the soil from the excavation is unusable, selected good soils to be imported. ដីប្រើប្រាស់សម្រាប់ផ្លូវវាងបណ្តោះអាសន្ន គិតទាំំងការងារបង្ហាប់កំរាស់មិនលើសពី១៥០មម។ បើដីដែលកាយមិនអាចប្រើប្រាស់បាន ត្រូវប្រើប្រាស់ដីដែលដឹកពីកន្លែងផ្សែងមកជំនួស។ | m3
5.4 | Supply graded granular backfill material on the surface layer of not less than 20 cm thickness including compaction. ក្រួសក្រាលសំរាប់ស្រទាប់ផ្ទៃលើមិនអោយតិចជាង២០សម គិតទាំងការបង្ហាប់។ | m3
5.5 | Supply and construct lean concrete for foundations. The thickness of the lean concrete shall be 10 cm or otherwise as specified in the drawing. The mix proportion for the lean concrete is 1:3:6 (in volume). The concrete should be mixed by using small concrete mixer and cast in situ. ប៉េតុងលីនសម្រាប់គ្រឹះ។ ប៉េតុងលីនត្រូវមានកំរាស់១០សម ឫយោងតាមបទដ្ឋានដែលបានណែនាំ។ ប៉េតុងត្រូវលាយក្នុងសមមាត្រមាឌ ១:៣:៦។ ប៉េតុងត្រូវបានលាយនឹងម៉ាស៊ីននៅការដ្ឋាន។ | m3
5.6 | Supply and place concrete (price without steel bars) - for headwalls, wing walls, cut off wall and aprons Concrete having a strength of F'c=25 MPa or the mixing proportion is 1:2:4. The work shall include weep holes wherever specified. ប៉េតុង (មិនមានសរសៃដែក) សម្រាប់ជញ្ជាំងខាងលើ,ស្លាប, ជញ្ជាំងកណ្តាល, និង​កម្រាលប៉េតុង ត្រូវមានភាពរឺង F'c=25 MPa ឬមានសមមាត្រមាឌ ១:២:៤។ ជញ្ជាំងគួរតែមានរន្ធមង្ហូរទឹក។ | m3
5.7 | Supply and construct High Tensile Steel Reinforcement for concrete structures (all diameters). The price shall include, cutting, bending, tying wire, fixing and waste from the cuts - all inclusive. ការសាងសង់ប៉េតុងដែលមានសរសៃដែក។ តម្លៃគិតបញ្ជូលទាំងការកាត់, ពត់, ចង, កែលំហរ និងការខូចខាងផ្សេងៗ។ | kg
5.8 | Supply and install concrete pipes including installation and sealing of the joints by morta 1:3 (in volume) as specified លូប៉េតុង គិតរូមទាំងការតំឡើង និងបិទផ្សារដោយស៊ីម៉ង់ត៍ ១:៣ ។
| Reinforced concrete pipe diameter 100cm លូមុខកាត់ ១០០សម | No
| Reinforced concrete pipe diameter 80 cm លូមុខកាត់៨០សម | No
| Reinforced concrete pipe diameter 60 cm លូមុខកាត់៦០សម | No
5.9 | Supply and install formwork: The price includes formwork installed all support, bracing, and other accessories and all inclusive. ការងារពុម្ព និងតំឡើង គិតរួមទាំងការងារផ្សេងៗទាក់ទងនឹងការងារពុម្ព។ | m2
5.10 | Supply and construct cement stone masonry work. Work covers the supply of the material and is place in courses with lean mix concrete/cement (or cement mortar). Stone size should not be less than 0.2 m2 surface. Priced, all complete based on the standard drawing included in the bid document. The actual drawing will be detailed in shop drawings prepared by the contractor ការងារប៉េតុងដែលលាយថ្មកាត់ស៊ីស។ ការងារគិតរូមមានទាំងការដឹកជញ្ជូន និងផ្គត់ផ្គង់។ ថ្មកាត់ស៊ីសមិនអោយមានទំហំតិចជាង ០.២ ម៉ែត្រការ៉េផ្ទៃ។ តម្លៃគិតបញ្ជូលទាំងអស់សម្រាប់ការងារពាក់ព័ន្ធ។ | m3
SUB TOTAL-ROAD FURNITURE-DRAINAGE STRUCTURE ការរចនាសោភ័ណភាព
IV | TURFING ក្រាលឫដាំស្មៅ
5.11 | Turfing/grass planting: The price shall include, ground preparation, supply the grass, plant and until end of the maintenance period ក្រាល ឫដាំស្មៅ គិតរូមទាំងការងារផ្សេងៗទាក់ទងនឹងការសម្អាត, ផ្គត់ផ្គង់ស្មៅ, ការដាំដុះ និងថៃទាំ។ | m2
5.12 | Tree planting: The price shall include, ground preparation, supply the tree, plant and until end of the maintenance period ការដាំដើមឈើ | No
SUB TOTAL-TURFING/PLAITING GRASS ការងារដាំដុះស្មៅផ្សេងៗ
Note: *Minimun Labour wage is US$ 8.5 /WD