## Lot 1
Lot 01 - Engineering Services for Technical Assessment Water Supply Infrastructures & Systems in the Cabo Delgado Province, Republic of Mozambique: Palma Sede Old system, Palma Sede area 4, Palma Sede area 5, Mute, Palma sede Manguna, Quionga and Quirinde PALMA
No | Description | Amount (MZN)
1 | Payment Milestone 1 - Upon deployment of assessment team to the site | 0
2 | Payment milestone 2: Upon the completion of the draft assessment report and acceptance by UNOPS . | 0
3 | Payment milestone 3: Upon the completion of the final assessment and acceptance by UNOPS | 0
Total in MZN including VAT |  | 0
Breakdown of Cost
Item | Description | No. Personnel | Unit of Measure | Proposed Qty / days | Cost Rate (MZN) | Cost (MZN)
1 | Milestone 1 Mobilization and logistics For site assessment
1.1 | Daily Subsistence Allowance (DSA) including accomodation, food and other related allowances- nr of people x days. (No. of man-days should not exceed 21 man-days) | 6 | man days | 21 |  | 0
1.2 | Daily Subsistence Allowance (DSA) including accomodation, food and other related allowances- nr of people x days. (No. of man-days should not exceed 21 man-days) | 1 | man days | 5 |  | 0
1.3 | Travel to Pemba | 7 | l.s. | 1 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0 | 5
| Sub Total Milestone 1 |  |  |  |  | 0
2 | Milestone 2 Key Personnel For Field Assessment Works and Preparation of Assessment Report
A) Site Assessment
2.1 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality) | 1 | man days | 5 |  | 0
2.2 | Mechanical Engineer | 1 | man days | 21 |  | 0
2.3 | Electrical Engineer | 1 | man days | 21 |  | 0
2.4 | Hydraulic Engineer | 1 | man days | 21 |  | 0
2.5 | Civil Engineer | 1 | man days | 21 |  | 0
2.6 | Environmental /HSSE Specialist | 1 | man days | 21 |  | 0
2.7 | Architect | 1 | man days | 5 |  | 0
2.8 | Surveyor Topography | 1 | man days | 21 |  | 0
2.9 | CAD Technicians | 1 | man days | 10 |  | 0
2.10 | Equipment : Theodolite surveying, GPS Cameras, Laptops, modem, Calculators, Measuring tape etc |  | LS |  |  | 0
B) Key Personnel For Preparing Draft Assessment Report
2.12 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality | 1 | man days | 5 |  | 0
2.13 | Mechanical Engineer | 1 | man days | 10 |  | 0
2.14 | Electrical Engineer | 1 | man days | 10 |  | 0
2.15 | Hydraulic Engineer | 1 | man days | 10 |  | 0
2.16 | Civil Engineer | 1 | man days | 10 |  | 0
2.17 | Structural Engineer | 1 | man days | 10 |  | 0
2.18 | Environmental /HSSE Specialist | 1 | man days | 10 |  | 0
2.19 | Architect | 1 | man days | 5 |  | 0
2.20 | Surveyor Topography | 1 | man days | 10 |  | 0
2.21 | CAD Technicians | 1 | man days | 10 |  | 0
2.22 | Stationary + reports printing | 1 | l.s | 1 |  | 0
C) Testing
Allow for testing of existing water supply network (for testing of leakages in exiting pipe lines and for testing of water quality).
2.23 | - Water quality tests (one per site) |  | No | 7 |  | 0
2.24 | - Leakge tests (If conditions allow, per setion of water supply network). A section is between two main valves. Assumed 10 per WSS |  | No | 70 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0
| Sub Total - Milestone 2 |  |  |  |  | 0
3 | Milestone 3 Key Personnel For Preparing Final Assement Report
3.1 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality | 1 | man days | 10 |  | 0
3.2 | Mechanical Engineer | 1 | man days | 29 |  | 0
3.3 | Electrical Engineer | 1 | man days | 29 |  | 0
3.4 | Hydraulic Engineer | 1 | man days | 29 |  | 0
3.5 | Civil Engineer | 1 | man days | 29 |  | 0
3.6 | Structural Engineer | 1 | man days | 10 |  | 0
3.7 | Environmental /HSSE Specialist | 1 | man days | 20 |  | 0
3.8 | Architect | 1 | man days | 10 |  | 0
3.9 | Surveyor Topography | 1 | man days | 15 |  | 0
3.10 | CAD Technicians | 1 | man days | 20 |  | 0
3.11 | Stationary + reports printing | 1 | l.s | 1 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0
| Sub Total - Milestone 3 |  |  |  |  | 0
* From Pemba to Palma, Airline and Transportation will be provided by UNOPS
* Leakage tests (If conditions allow one per site for entire network)

## Lot 2
Lot 02 - Engineering Services for Technical Assessment Water Supply Infrastructures & Systems in the Cabo Delgado Province, Republic of Mozambique: Mocimboa da Praia sede, Diaca, Mbau in MOCIMBAO DE PRAIA and Base Ntchinga in MUIDEMBE
No | Description | Amount (MZN)
1 | Payment Milstone 1 - Upon deplyoment of assessment team to the site | 0
2 | Payment milestone 2: Upon the completion of the draft assessment report and acceptance by UNOPS . | 0
3 | Payment milestone 3: Upon the completion of the final assessment and acceptance by UNOPS | 0
Total in MZN including VAT |  | 0
Breakdown of Cost
Item | Description | No. Personnel | Unit of Measure | Proposed Qty / days | Cost Rate (MZN) | Cost (MZN)
1 | Milestone 1 Mobilization and logistics For site assessment
1.1 | Daily Subsistence Allowance (DSA) including accomodation, food and other related allowances- nr of people x days. (No. of man-days should not exceed 21 man-days) | 6 | man days | 15 |  | 0
1.2 | Daily Subsistence Allowance (DSA) including accomodation, food and other related allowances- nr of people x days. (No. of man-days should not exceed 21 man-days) | 1 | mandays | 3 |  | 0
1.2 | Travel to Pemba | 6 | l.s. | 1 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0 | 5
| Sub Total Milestone 1 |  |  |  |  | 0
2 | Milestone 2 Key Personnel For Field Assessment Works and Preparation of Assessment Report
A) Site Assessment
2.1 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality) | 1 | man days | 3 |  | 0
2.2 | Mechanical Engineer | 1 | man days | 15 |  | 0
2.3 | Electrical Engineer | 1 | man days | 15 |  | 0
2.4 | Hydraulic Engineer | 1 | man days | 15 |  | 0
2.5 | Civil Engineer | 1 | man days | 15 |  | 0
2.6 | Environmental /HSSE Specialist | 1 | man days | 15 |  | 0
2.7 | Architect | 1 | man days | 3 |  | 0
2.8 | Surveyor Topography | 1 | man days | 15 |  | 0
2.9 | CAD Technicians | 1 | man days | 15 |  | 0
2.10 | Equipment : Theodolite surveying, GPS Cameras, Laptops, modem, Calculators, Measuring tape etc |  | LS |  |  | 0
B) Key Personnel For Preparing Draft Assessment Report
2.12 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality | 1 | man days | 10 |  | 0
2.13 | Mechanical Engineer | 1 | man days | 10 |  | 0
2.14 | Electrical Engineer | 1 | man days | 10 |  | 0
2.15 | Hydraulic Engineer | 1 | man days | 10 |  | 0
2.16 | Civil Engineer | 1 | man days | 10 |  | 0
2.17 | Structural Engineer | 1 | man days | 10 |  | 0
2.18 | Environmental /HSSE Specialist | 1 | man days | 10 |  | 0
2.19 | Architect | 1 | man days | 5 |  | 0
2.20 | Surveyor Topography | 1 | man days | 10 |  | 0
2.21 | CAD Technicians | 1 | man days | 10 |  | 0
2.22 | Stationary + reports printing | 1 | l.s | 1 |  | 0
C) Testing
Allow for testing of existing water supply network (for testing of leakages in exiting pipe lines and for testing of water quality).
2.23 | - Water quality tests (one per site) |  | No | 4 |  | 0
2.24 | - Leakge tests (If conditions allow, per setion of water supply network). A section is between two main valves. Assumed 10 per WSS |  | No | 35 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0
| Sub Total - Milestone 2 |  |  |  |  | 0
3 | Milestone 3 Key Personnel For Preparing Final Assement Report
3.1 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality | 1 | man days | 10 |  | 0
3.2 | Mechanical Engineer | 1 | man days | 20 |  | 0
3.3 | Electrical Engineer | 1 | man days | 20 |  | 0
3.4 | Hydraulic Engineer | 1 | man days | 20 |  | 0
3.5 | Civil Engineer | 1 | man days |  |  | 0
3.6 | Structural Engineer | 1 | man days | 10 |  | 0
3.7 | Environmental /HSSE Specialist | 1 | man days | 10 |  | 0
3.8 | Architect | 1 | man days | 5 |  | 0
3.9 | Surveyor Topography | 1 | man days | 5 |  | 0
3.10 | CAD Technicians | 1 | man days | 15 |  | 0
3.11 | Stationary + reports printing | 1 | l.s | 1 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0
| Sub Total - Milestone 3 |  |  |  |  | 0
* From Pemba to Palma, Airline and Transportation will be provided by UNOPS
* Leakage tests (If conditions allow one per site for entire network)

## Lot 3
Lot 03 - Engineering Services for Technical Assessment Water Supply Infrastructures & Systems in the Cabo Delgado Province, Republic of Mozambique: Bilibiza and Quissanga Cede in QUISSANGA
No | Description | Amount (MZN)
1 | Payment Milstone 1 - Upon deplyoment of assessment team to the site | 0
2 | Payment milestone 2: Upon the completion of the draft assessment report and acceptance by UNOPS . | 0
3 | Payment milestone 3: Upon the completion of the final assessment and acceptance by UNOPS | 0
Total in MZN including VAT |  | 0
Breakdown of Cost
Item | Description | No. Personnel | Unit of Measure | Proposed Qty / days | Cost Rate (MZN) | Cost (MZN)
1 | Milestone 1 Mobilization and logistics For site assessment
1.1 | Daily Subsistence Allowance (DSA) including accomodation, food and other related allowances- nr of people x days. (No. of man-days should not exceed 21 man-days) | 6 | man days | 10 |  | 0
1.2 | Daily Subsistence Allowance (DSA) including accomodation, food and other related allowances- nr of people x days. (No. of man-days should not exceed 21 man-days) | 1 | mandays | 2 |  | 0
1.2 | Travel to Pemba | 6 | l.s. | 1 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0 | 5
| Sub Total Milestone 1 |  |  |  |  | 0
2 | Milestone 2 Key Personnel For Field Assessment Works and Preparation of Assessment Report
A) Site Assessment
2.1 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality) | 1 | man days | 2 |  | 0
2.2 | Mechanical Engineer | 1 | man days | 10 |  | 0
2.3 | Electrical Engineer | 1 | man days | 10 |  | 0
2.4 | Hydraulic Engineer | 1 | man days | 10 |  | 0
2.5 | Civil Engineer | 1 | man days | 10 |  | 0
2.6 | Environmental /HSSE Specialist | 1 | man days | 10 |  | 0
2.7 | Architect | 1 | man days | 3 |  | 0
2.8 | Surveyor Topography | 1 | man days | 10 |  | 0
2.9 | CAD Technicians | 1 | man days | 5 |  | 0
2.10 | Equipment : Theodolite surveying, GPS Cameras, Laptops, modem, Calculators, Measuring tape etc |  | LS |  |  | 0
B) Key Personnel For Preparing Draft Assessment Report
2.12 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality | 1 | man days | 10 |  | 0
2.13 | Mechanical Engineer | 1 | man days | 10 |  | 0
2.14 | Electrical Engineer | 1 | man days | 10 |  | 0
2.15 | Hydraulic Engineer | 1 | man days | 10 |  | 0
2.16 | Civil Engineer | 1 | man days | 10 |  | 0
2.17 | Structural Engineer | 1 | man days | 10 |  | 0
2.18 | Environmental /HSSE Specialist | 1 | man days | 10 |  | 0
2.19 | Architect | 1 | man days | 3 |  | 0
2.20 | Surveyor Topography | 1 | man days | 5 |  | 0
2.21 | CAD Technicians | 1 | man days | 5 |  | 0
2.22 | Stationary + reports printing | 1 | l.s | 1 |  | 0
C) Testing
Allow for testing of existing water supply network (for testing of leakages in exiting pipe lines and for testing of water quality).
2.23 | - Water quality tests (one per site) |  | No | 2 |  | 0
2.24 | - Leakge tests (If conditions allow, per setion of water supply network). A section is between two main valves. Assumed 10 per WSS |  | No | 10 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0
| Sub Total - Milestone 2 |  |  |  |  | 0
3 | Milestone 3 Key Personnel For Preparing Final Assement Report
3.1 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality | 1 | man days | 5 |  | 0
3.2 | Mechanical Engineer | 1 | man days | 20 |  | 0
3.3 | Electrical Engineer | 1 | man days | 20 |  | 0
3.4 | Hydraulic Engineer | 1 | man days | 20 |  | 0
3.5 | Civil Engineer | 1 | man days | 20 |  | 0
3.6 | Structural Engineer | 1 | man days | 20 |  | 0
3.7 | Environmental /HSSE Specialist | 1 | man days | 20 |  | 0
3.8 | Architect | 1 | man days | 3 |  | 0
3.9 | Surveyor Topography | 1 | man days | 5 |  | 0
3.10 | CAD Technicians | 1 | man days | 10 |  | 0
3.11 | Stationary + reports printing | 1 | l.s | 1 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0
| Sub Total - Milestone 3 |  |  |  |  | 0
* From Pemba to Palma, Airline and Transportation will be provided by UNOPS
* Leakage tests (If conditions allow one per site for entire network)

## Lot 4
Lot 04 - Engineering Services for Technical Assessment Water Supply Infrastructures & Systems in the Cabo Delgado Province, Republic of Mozambique: Mengueleua - MUIDUMBE and Chai MACOMIA
No | Description | Amount (MZN)
1 | Payment Milstone 1 - Upon deplyoment of assessment team to the site | 0
2 | Payment milestone 2: Upon the completion of the draft assessment report and acceptance by UNOPS . | 0
3 | Payment milestone 3: Upon the completion of the final assessment and acceptance by UNOPS | 0
Total in MZN including VAT |  | 0
Breakdown of Cost
Item | Description | No. Personnel | Unit of Measure | Proposed Qty / days | Cost Rate (MZN) | Cost (MZN)
1 | Milestone 1 Mobilization and logistics For site assessment
1.1 | Daily Subsistence Allowance (DSA) including accomodation, food and other related allowances- nr of people x days. (No. of man-days should not exceed 21 man-days) | 6 | man days | 10 |  | 0
1.2 | Daily Subsistence Allowance (DSA) including accomodation, food and other related allowances- nr of people x days. (No. of man-days should not exceed 21 man-days) | 1 | mandays | 2 |  | 0
1.2 | Travel to Pemba | 6 | l.s. | 1 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0 | 5
| Sub Total Milestone 1 |  |  |  |  | 0
2 | Milestone 2 Key Personnel For Field Assessment Works and Preparation of Assessment Report
A) Site Assessment
2.1 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality) | 1 | man days | 2 |  | 0
2.2 | Mechanical Engineer | 1 | man days | 10 |  | 0
2.3 | Electrical Engineer | 1 | man days | 10 |  | 0
2.4 | Hydraulic Engineer | 1 | man days | 10 |  | 0
2.5 | Civil Engineer | 1 | man days | 10 |  | 0
2.6 | Environmental /HSSE Specialist | 1 | man days | 10 |  | 0
2.7 | Architect | 1 | man days | 3 |  | 0
2.8 | Surveyor Topography | 1 | man days | 10 |  | 0
2.9 | CAD Technicians | 1 | man days | 5 |  | 0
2.10 | Equipment : Theodolite surveying, GPS Cameras, Laptops, modem, Calculators, Measuring tape etc |  | LS |  |  | 0
B) Key Personnel For Preparing Draft Assessment Report
2.12 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality | 1 | man days | 10 |  | 0
2.13 | Mechanical Engineer | 1 | man days | 10 |  | 0
2.14 | Electrical Engineer | 1 | man days | 10 |  | 0
2.15 | Hydraulic Engineer | 1 | man days | 10 |  | 0
2.16 | Civil Engineer | 1 | man days | 10 |  | 0
2.17 | Structural Engineer | 1 | man days | 10 |  | 0
2.18 | Environmental /HSSE Specialist | 1 | man days | 10 |  | 0
2.19 | Architect | 1 | man days | 3 |  | 0
2.20 | Surveyor Topography | 1 | man days | 5 |  | 0
2.21 | CAD Technicians | 1 | man days | 5 |  | 0
2.22 | Stationary + reports printing | 1 | l.s | 1 |  | 0
C) Testing
Allow for testing of existing water supply network (for testing of leakages in exiting pipe lines and for testing of water quality).
2.23 | - Water quality tests (one per site) |  | No | 2 |  | 0
2.24 | - Leakge tests (If conditions allow, per setion of water supply network). A section is between two main valves. Assumed 10 per WSS |  | No | 10 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0
| Sub Total - Milestone 2 |  |  |  |  | 0
3 | Milestone 3 Key Personnel For Preparing Final Assement Report
3.1 | Senior Project manager/Coordinator (Civil / Mechanical Eng. with Water Resources speciality | 1 | man days | 5 |  | 0
3.2 | Mechanical Engineer | 1 | man days | 20 |  | 0
3.3 | Electrical Engineer | 1 | man days | 20 |  | 0
3.4 | Hydraulic Engineer | 1 | man days | 20 |  | 0
3.5 | Civil Engineer | 1 | man days | 20 |  | 0
3.6 | Structural Engineer | 1 | man days | 20 |  | 0
3.7 | Environmental /HSSE Specialist | 1 | man days | 20 |  | 0
3.8 | Architect | 1 | man days | 3 |  | 0
3.9 | Surveyor Topography | 1 | man days | 5 |  | 0
3.10 | CAD Technicians | 1 | man days | 10 |  | 0
3.11 | Stationary + reports printing | 1 | l.s | 1 |  | 0
| Sub total |  |  |  |  | 0
| Overhead and profit |  | % |  |  | 0
| Sub Total - Milestone 3 |  |  |  |  | 0
* From Pemba to Palma, Airline and Transportation will be provided by UNOPS
* Leakage tests (If conditions allow one per site for entire network)

## Schedule of Day Works
Schedule of Day Rate
Breakdown of Cost
Item | Description | No. Personnel | Unit of Measure | Qty | Cost Rate (MZN) | Cost (MZN)
1 | General - DSA & Equipment
1.1 | Travel (ariline ticket to Pemba) | 1 | No | 1 |  | 0
1.2 | Daily Subsistence Allowance (DSA) including accomodation, food and other related allowances- nr of people x days. (No. of man-days should not exceed 21 man-days) | 1 | day | 1 |  | 0
1.3 | Equipment |  | No. | 1 |  | 0
| Sub Total |  |  |  |  | 0
2 | Support to Key Personnel For Field Assessment Works
2.1 | Unskilled helper | 1 | man days | 1 |  | 0
2.2 | Skilled helper | 1 | man days | 1 |  | 0
2.3 | Local fees (to be paid by the contractor) | 1 | man days | 1 |  | 0
2.4 | [5 empty] | 0
| Sub Total |  |  |  |  | 0
3 | Testing
| Allow for testing of existing water supply network (for testing of leakages in exiting pipe lines and for testing of water quality). |  |  |  |  | 0
| - Water quality tests - Leakage tests - 5 in no. | 1 | No | 1 |  | 0
2.24 | - Leakge tests (If conditions allow, per setion of water supply network). A section is between two main valves. Assumed 10 per WSS |  | No | 1 |  | 0
* From Pemba to Palma, Airline and Transportation will be provided by UNOPS