## WP-Road work
Annex IIF Work Plan for rehabilitation of rural road in Srae Khvav Commune, Angkor Chum district, Siem Reap Province, ITB No 06-2023
The bar chart below represents a simple work program only. Bidders are advised to adopt this format, but submit their own programme on at least A-3 size sheets
No. | Description | Works |  | 2024-01-01 |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01 | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  | 2024-07-01
|  | Unit | Qty. | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
I | GENERAL ITEMS
| Contractor mobilisation, process insurance for workers, provision of Safety and health, installation of project signboards | Ls | 1
2 | SITE CLEARANCE WORKS
2.1 | Site Clearing and removal within the limits of working area (road formation) all vegetation, surface debris, scattered stones and removal of top soil (where is required etc). All wasted material shall be disposed to approved dumping areas. The work shall be carried out by manual labour
a | Light bush clearing grass clearing | m2 | 1800
II | ROAD WORK
2 | SITE CLEARANCE WORKS
2.2 | Site Clearing and removal of grass, and bushes within the limits of working area (road formation) all vegetation, surface debris, scattered stones. All wasted material shall be disposed to approved dumping areas. The work shall be carried out by manual labour
a | Light bush clearing grass clearing | m2 | 13030
b | Heavy bush clearing | m2 | 6560
3 | EARTH WORKS
The work shall include: Supply material, Spreading, levelling, trim, all labour, equipment related to transporting and compaction. Finishing and grading to any cross-falls (camber), or slopes that may be required. Excess and Unsuitable soil must be removed and dumped in authorized sites as instructed by the project engineer.
3.3 | Fill embankment by transported soil. Supply the selected soil, fill, spread, level and compact by roller in layers not exceeding 150 mm, to 95% of maximum dry density, using approved and suitable filling material. Spreading soil for levelling shall be done by labour. | m3 | 978.11
3.4 | Filling embankment by excavated soil from surrounding borrow pits (by manual labour). Excavate, haul (no exceeding 50m hauling distance), fill, spread, level and compact by roller in layers not exceeding 150 mm, to 95% of maximum dry density, using approved and suitable filling material. | m3 | 6424.73
3.5 | Excavate for side drain by manual labour, to be completed as specified in the typical drawing & to the Project Engineer's satisfaction. Excess and unsuitable soil must be removed from excavated side drain of a minimum 1.5m. Excavated soil found suitable for re-use shall be spread and compacted as instructed by project engineer. | m3 | 301.95
4 | ROAD PAVEMENT AND SURFACE
The works Include surfaces preparation, samples, Laboratory tests, compaction, watering. The works shall be executed as Shown in the typical draining and specifications to the satisfaction of the project Engineer. Rate shall include all related equipment, labour, transportation, compaction, finishing etc
4.1 | Gravel wearing course Supply and compact the gravel layer laid on compacted earthwork. The gravel layer shall be spread by labour to the designed level and cross fall(7%) as stated in the typical drawing. Compaction shall be done by roller after the gravel is spread to achieve not less than 100% of maximum dry density at optimum moisture as determined by ASTM D 1556 | m3 | 2910
IV | TURFING
5.11 | Turfing/grass planting: The price shall include, ground preparation, supply the grass, plant and until end of the maintenance period | m2 | 9700
5.12 | Tree planting: The price shall include, ground preparation, supply the tree, plant and until end of the maintenance period | No | 1215.5

## WP-culver single row
Annex IIF Work Plan for culvert construction(1 unit dia80cm single row) on the road in Srae Khvav Commune, Angkor Chum district, Siem Reap Province, ITB No 06-2023
The bar chart below represents a simple work program only. Bidders are advised to adopt this format, but submit their own programme on at least A-3 size sheets
No. | Description | Works |  | 2024-01-01 |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01 | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  | 2024-07-01
|  | Unit | Qty. | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
2.1 | Excavation for foundations Excess and unsuitable soil removed, deposited, or reused at locations authorized by the Project Engineer. Excavated soil found suitable for re-use stored at the appropriate location for backfilling. | m3 | 25
2.2 | Backfill around foundations from selective excavated materials, including compaction in layers not exceeding 150mm thickness. Where the soil from the excavation is unusable, selected good soils to be imported. | m3 | 7
2.4 | Supply and construct lean concrete for foundations. The thickness of the lean concrete shall be 10 cm or otherwise specified. The mix proportion for the lean concrete is 1:3:6 (in volume). The concrete should be mixed by using small concrete mixer and cast in situ. | m3 | 2.69
2.5 | Supply and place concrete (price without steel bars) - for headwalls, wing walls, cut off wall and aprons Concrete having a strength of F'c=25 MPa or the mixing proportion is 1:2:4. The work shall include weep holes wherever specified. | m3 | 4.95
2.6 | Supply and construct High Tensile Steel Reinforcement for concrete structures (all diameters). The price shall include, cutting, bending, tying wire, fixing and waste from the cuts - all inclusive. | kg | 165
2.7 | Supply and install concrete pipes including installation and sealing of the joints by morta 1:4 (in volume) as specified
| Reinforced concrete pipe diameter 80 cm | No | 6
2.8 | Supply and install formwork: The price includes formwork installed all support, bracing, and other accessories and all inclusive. | m2 | 11.72

## WP culvert Doube row
Annex IIF Work Plan for culvert construction(3 units dia80cm double rows) on the road in Srae Khvav Commune, Angkor Chum district, Siem Reap Province, ITB No 06-2023
The bar chart below represents a simple work program only. Bidders are advised to adopt this format, but submit their own programme on at least A-3 size sheets
No. | Description | Works |  | 2024-01-01 |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01 | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  | 2024-07-01
|  | Unit | Qty. | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
2.1 | Excavation for foundations Excess and unsuitable soil removed, deposited, or reused at locations authorized by the Project Engineer. Excavated soil found suitable for re-use stored at the appropriate location for backfilling. | m3 | 98.49
2.2 | Backfill around foundations from selective excavated materials, including compaction in layers not exceeding 150mm thickness. Where the soil from the excavation is unusable, selected good soils to be imported. | m3 | 10
2.4 | Supply and construct lean concrete for foundations. The thickness of the lean concrete shall be 10 cm or otherwise specified. The mix proportion for the lean concrete is 1:3:6 (in volume). The concrete should be mixed by using small concrete mixer and cast in situ. | m3 | 11.46
2.5 | Supply and place concrete (price without steel bars) - for headwalls, wing walls, cut off wall and aprons Concrete having a strength of F'c=25 MPa or the mixing proportion is 1:2:4. The work shall include weep holes wherever specified. | m3 | 18.9
2.6 | Supply and construct High Tensile Steel Reinforcement for concrete structures (all diameters). The price shall include, cutting, bending, tying wire, fixing and waste from the cuts - all inclusive. | kg | 632.2995
2.7 | Supply and install concrete pipes including installation and sealing of the joints by morta 1:4 (in volume) as specified
| Reinforced concrete pipe diameter 80 cm | No | 36
2.8 | Supply and install formwork: The price includes formwork installed all support, bracing, and other accessories and all inclusive. | m2 | 41.67