- UNITED NATIONS INDUSTRIAL DEVELOPMENT ORGANIZATION

TERMS OF REFERENCE (TOR)

Development of the Nigeria Industrial Revolution Plan (NIRP) Web site and data management system

UNIDO Project No. 140070 - Nigeria

13 July 2015

- Background Information

The project addresses the capacity development needs of the Federal Ministry of Industry, Trade and Investment (FMITI) to lead and monitor the implementation of selected elements of Nigeria Industrial Revolution Plan (NIRP), in collaboration with its parastatals as well as Manufacturer’s Association of Nigeria (MAN) and the National Bureau of Statistics (NBS). Specifically, the project will focus on identifying and developing some fundamental skills and tools needed for supporting implementation of selected NIRP actions, setting up institutional collaboration and monitoring mechanisms and a system of industrial performance indicators that will inform policy makers and NIRP stakeholders on progress achieved as implementation proceeds.

More specifically, the project aims to support NIRP implementation in six sub-sectors: 1) Leather and leather products; 2) Garments; 3) Automotive; 4) Steel; 5) Petrochemicals; and 6) Housing construction.  For each sub-sector selected, one or more enabler areas from among infrastructure, skills, investment climate, standards, local patronage, and finance will be identified for capacity development interventions at sub-sector and related enabler area for FMITI, and representatives of parastatals and the private sector.

Capacity building interventions focusing on selected sectors and enablers may be designed in the form of on-the-job or classroom training, guided preparation of study reports and recommendations on legal and regulatory matters on trade and industry promotion, consultation and partnership events, study visits within the country and abroad, preparation and launching of investment promotion events/campaigns, formulation of investment briefs, investment project assessment, survey design and commissioning, statistical analysis, project management, use of ICT at the work place, industrial zone planning, management, and governance structures, venture capital, innovative financial instruments, WTO rules, intellectual property matters related to sectors selected, gender perspectives, etc. Exact nature, topic and modality of the interventions will be designed and agreed during the inception phase and reviewed in each planning period for revisions, as deemed necessary.

The project will also assist FMITI and MAN to set up an Industrial Performance Monitoring System (IPMS) to monitor progress achieved in NIRP implementation. Operationalization of the IPMS will best be achieved through institutional collaboration between FMITI, NBS, MAN, Central Bank of Nigeria, other financial institutions, and Ministries such as the Ministry of Finance (e.g. corporate revenue statistics), Agriculture and Rural Development, Labour and Productivity (e.g. jobs created) etc. The project will assist MAN with the computerization of its regular data collection, analysis and reporting from its membership along the lines of its current manufacturers surveys; and, will assist and advise NBS in the production of indices of industrial production (IIP).

This assignment is for the development of tools for coordination, monitoring and information dissemination.  These include:

i.	Management and knowledge sharing tool;

ii.	NIRP Website for:

•	Dissemination of news and information on the NIRP, its activities, accomplishments; in particular providing evidence of how some of the measures and incentives benefit the overall economy and consumers in the long run;

•	Inter-organizational documentation and correspondence repository and knowledge sharing tool;

•	Database of Ministry and other institutions’ staff involved in NIRP, their respective skills and experience, training and capacity building through the project.

iii.	NIRP Monitoring System based on the performance data and CEO perceptions of the (approx.) 30 largest companies in each of the NIRP sub-sectors.  This group of companies, referred to as the NIRP-500, will serve as the reference group for assessing the health of the Nigerian industrial sector, identifying trends and measuring the rates of change of critical indicators, as well as trying to build some forward oriented indicators with predictive capacities.

The NIRP-500 will be selected carefully based on criteria to be determined jointly with the NIRP Secretariat.  This group of companies are expected to perceive selection into the NIRP-500 as a privilege on the basis of their representative attributes and importance to the Nigerian economy.  The list will be widely circulated, and, each member will be recognized at the highest level in the Federal Government.  The List will be periodically reviewed for changes involving deletions and new entries based on growth and relative importance.

These companies will be part of a system whereby their basic operational data and readings of the economy will be collected on a quarterly basis through a dedicated on-line system and presented on a platform that will have customizable data analysis and visualization functionalities.  The analysis and visualization tool will be fully accessible to the 500 companies that are part of the system, and reports generated by the Secretariat will be accessible by the general public.  The data analysis will reveal the rate of growth of sectors in terms of employment, output, exports, value addition, new investments, etc. and will allow users and analysts the possibility to assess the impact of the NIRP initiatives on the different industrial sub-sectors in many ways.

iv.	Indices of industrial production, based on a broader industrial survey based on a representative sample and conducted by the NBS and when available, will also be used to provide additional visibility on the health and growth trajectories of the Nigerian industrial sub-sectors.

v.	Other data systems that are relevant for improving the analytical potential of the NIRP-500 Monitoring System will be integrated into what may become a comprehensive database on the Nigerian industrial sector.  These will include:

•	The MAN periodic survey of members (see above);

•	The Central Bank of Nigeria (CBN) data on largest foreign investments and largest importers and exporters;

•	The Internal Revenue Service (IRS) Large Taxpayers data;

•	Corporate Affairs Corporation (CAC) data on registration of businesses;

•	Data from spot surveys on special topics conducted using the on-line system.

- Objective of the present Terms of Reference

The objective of the contract is for designing the IPMS, which will consist of three phases:

- Public Website which will be the face of the NIRP to the general public to ensure that the objectives and methods of the NIRP are understood, the steps being taken to achieve those objectives are clearly spelled out.  This will be the means through which the NIRP Secretariat will disseminate news and information on the NIRP, its activities, accomplishments.  In particular providing evidence of how some of the measures taken and incentives given to sub-sectors benefit the overall economy and consumers in the long run.  It will also have an inter-organizational documentation and correspondence repository and knowledge sharing tool as well as a database of Ministry and other institutions’ staff involved in NIRP, their respective skills and experience, training and capacity building through the project.

This first phase includes the development of a Content Management System (CMS) based on readily available, off-the-shelf software for the website. The following access would be available:

a. Public Access

b. Client (IID) Access

This website would have the following functions;

- Public Interface: Here the general public would have access to view the contents published on the website. The content will include the basic organizational details and any other information the NIRP Secretariat wishes to publish on the Website.  The Project and the Secretariat will provide the initial Sitemap to be used.

- CMS Administration: This part involves the content management system. Here the client (IID) would be able to create, edit, upload and manage content on the website. CMS software to be used will be selected to ensure simple and easy administration functionalities.

- On-line data collection system for compiling data, based on a questionnaire, from 500 companies in Nigeria selected due to them being among the largest companies in each of the NIRP priority sub-sectors.  The data collection system will be used on a quarterly basis and will also be used by MAN to conduct their survey of member manufacturers.

This Module will contain a data collection and collation environment. It will allow for data to be captured and aggregated. Here, selected companies (NIRP500) would be able to create user accounts and enter specific data that would be determined by the questionnaire.  Such data would include:

- Category and Nature of Business

- Sub Sector, coded by ISIC version 4,

- Product Line/Service, coded by ISIC version 4,

- Staff strength,

- Turnover,

- Investments,

- Capacity utilization, etc.

This information will have automatic checking functions for completeness and consistency before being saved on the portal.  The data storage architecture has to be designed as a cube to ensure proper cross tabulations and generation of compound variables.  The design of the architecture, the Meta data and error checking systems is a key part of this phase and ensures easy progress in the next phase.  The design will ensure robust and flexible search criteria; develop the Application Programming Interfaces for accessing the data in different databases; design the testing infrastructure for the databases and test the APIs to ensure that the data access components are working as intended, and design the replication systems.

- Data analysis and visualization tool, which will be the back-end for data analysis, aggregation, graphical display, data processing, reports generating and export and import.  This also serves as the main repository of the entire data captured on the portal.  This section would have abilities to integrate other databases securely with all functionalities of the portal being applied to the database.  Report Generation should be able to generate different types of reports. The graphical representation of data, user-friendly infographics are to be provided. The reports should be generated and exported to any type of document format as stated by client.

- Main Tasks

The tasks are shown in the table below:

| Main tasks | Concrete/ Measurable Outputs to be achieved | Estimated distribution of effort (in %) | Location |
| --- | --- | --- | --- |
| - Design the NIRP web site in accordance with the design parameters and functionalities specified. The design should be cognizant of the low bandwidth access to most users. The design should also take into consideration the expansions that are planned in subsequent phases. | Look and feel of the web site approved | - 15% | - Abuja |
| - Once the design is finalized, build the site and test that all the required functionalities are available and links to other sources are established. | Website functioning as foreseen |  |  |
| - Ensure debugging through extensive testing and train staff to maintain and update the web site. | Website up and running and public is able to access all information |  |  |
| - Ensure that the hardware, security, maintenance and hosting services are robust and support will be available 24/7 | Website is safe from hacking and other attacks and not subject to any down time. |  |  |
| - Develop the concept for the data collection system, looking at all options including download-fill-upload, on-line fill, email, etc., to select the option that is most suitable given the internet connectivity of most users, security issues, cost effectiveness, robustness, ease of use for companies. | Data collection method agreed upon | - 10% |  |
| - Test the usability and acceptability of the proposed concept by building a prototype (an alpha version) and asking a small group of test users to evaluate. | Design of system finalized | - 20% |  |
| - Once design is finalized, build with back-up systems, help menus for users, data entry checking systems, and secure storage in the appropriate manner. | System fully functional |  |  |
| - Thoroughly debug the system and include any functionality that may be deemed necessary in the course of testing. Train users to operate the system and to provide on-line support to those filling in the questionnaires. | System operational |  |  |
| - Develop the database internal architecture of the Data Engine, which includes creation of databases, tables, views, stored procedures, triggers, cursors. Define and design the security architecture for the data engine component. | Internal architecture for the Data Engine Database | - 15% |  |
| - Develop the API (interfaces) to access the data in the different databases | Database Design | - 5% |  |
| - Provide Database optimization that abides by the standards set by the quality assurance | API Documentation on the Data Engine Database | - 5% |  |
| - Develop the concept for the data analysis and visualization tool, developing approaches to visualizing all possible relationships between the data (those that make sense). | Analysis and visualization tool developed as concept | - 20% | - Abuja and other cities, as needed |
| - Create the tools that will be used for the visualization and develop the querying protocols | All components assembled |  |  |
| - Develop data access security interfaces for the Data Engine | Security ensured |  |  |
| - Build and debug the system. Train users and provide constant debugging service during operations. Three levels of access assured. | System operational and reports can be generated with collected data |  |  |
| - Provide hosting, maintenance and security services on a yearly basis and provide debugging for issues due to programming. There should be no limit on the number of users. | System operations are secure and fully accessible by all levels of users. | - 10% | - Abuja |
| - Provide necessary Quality Assurance (QA) and staging of various versions. Develop testing protocols. | Quality standards set and tested for at every stage |  |  |
| - Provide full documentation for all phases of the project justifying all decisions, actions and laying out the final designs | Full documentation received |  |  |

- Deliverables and timetable

The deliverables and associated deadlines are shown in the table below:

| Deliverables | Deadline |
| --- | --- |
| - Plan of Execution: - Deliver a detailed plan specifying each step, each output and delivery date - Establish decision points for discussions and final decisions on designs and specifications | Contract signature date + 5 calendar days |
| - Web-site design and mock up for demo and finalization: - Design based on inputs from NIRP project teams - Final approval for next stage | Contract signature date + 20 days |
| - Beta version of web-site for testing and debugging: - All components are functional - Test with selected inputs | Contract signature date + 35 days |
| - Operational version of website (ver. 1) up and running: - Ready for fine tuning with actual data and documents - Training users to populate and update the site | Contract signature date + 50 days |
| - Data collection plan: - Concept - Options and fall-back scenarios - Selection of tools and systems | Contract signature date + 55 days |
| - Beta version of data collection system for testing: - On-line data collection system using the provided questionnaire tested on selected users for ease of use and functionality - Error checking and flagging / auto correcting systems in place for testing - Data importing or transferring system for moving cleared data into the database also in place for testing | Contract signature date + 85 days |
| - Operational version of data collection system (ver. 1): - Bug free system ready for deployment - Monitoring mechanism in place to ensure bugs are identified and remedied quickly | Contract signature date + 100 days |
| - Database design: - Based on a detailed requirements for how the data will be manipulated, used for secondary calculations and queried, a database design that will allow these tasks to be completed in the most efficient manner | Contract signature date + 125 days |
| - Testing with query scenarios: - Once design is approved, build and test the database - Ensure stringent quality assurance and security systems - Stability, avoidance of nonsensical calculations and tabulations, consistency, speed and efficiency | Contract signature date + 145 days |
| - Final version delivered: - Final improvements and debugging, using real data | Contract signature date + 165 days |
| - Data visualization and reporting concepts developed: - Specs to be worked out with the user team - Design of visuals | Contract signature date + 170 days |
| - Design of data visualization system specifying tools: - Mock-up of system showing how different tabulations (2, 3, and up to 4 dimensions) will be represented | Contract signature date + 185 days |
| - Beta system for testing: - Test system with real data and debug, set scales, improve visuals based on how real data is presented | Contract signature date + 215 days |
| - Operational system fully functional with real data: - Help files and definitions of variables to assist users in interpreting their results - Report generating systems to convert query visuals into Word or PDF format with report format design and text input options - Training for operators and trainers - Check and validate user manual to be prepared by the trained trainers. | Contract signature date + 250 days |
| - System hosted at a secure location with high-speed connection, continuous operation, security systems, automatic backing up and essential software updates. Annual contract to be quoted separately on an annual basis. |  |

- Qualifications and skills required

The contractor’s team will consist of and perform as a minimum the following:

- One Team Leader/Manager

Senior IT expert, having at least 10 years of experience with system development and project leadership in:

- Developing technical specifications, developmental plans, strategies and working documents for the development teams.

- Leading the development team in architecture & design and come up with necessary tools that fit in the end-to-end automation framework

- Developing necessary testing protocols and directly manage the final testing and roll out of the system.

- Database expert to design, build, install, database systems to user specs.

- Web applications expert to design the online data acquisition system and the web site.

- Security architecture and Quality Assurance expert to ensure the architecture of the system incorporates industry standard security measures and facilities and that the whole system meets industry level quality standards.

- Other requirements

The bidder will:

- Provide the detailed CVs of staff offered for each of the positions listed under item 5 above; if more than one person is offered for any of the positions, CVs of all staff will be provided;

- Provide, against the list of deliverables, the name(s) of his staff who will be responsible for the deliverable;

- Describe in detail how the work will be conducted, how progress will be communicated and how quality assurance will be guaranteed, in a way that confirms his full understanding of the content of the deliverables expected in this TOR; and specify the industry standards that the systems will meet with respect to quality and security.

- Provide proposals on technology options for the different phases of the project;

- Provide information on how the systems built and installed will be assured of continued debugging and upgrading as required;

- Be an information services provider registered in Nigeria, and provide proof of registration for legally doing business in the country;

- Ensure that the Team Leader/Manager is available through electronic mail and telephone, within 4 hours after being contacted, and available for face-to-face discussions when requested by the Project Manager, the Lead Consultant and/or the Director of IDID upon prior arrangement of a meeting;

- Offer site hosting in a secure location with all security, upgrading and back-up systems in place;

- Provide 3 references of similar work undertaken, with names and contact information;

- Offer warranty services for 12 months following the date of the final payment;

- Confirm bidder’s agreement to the payment schedule provided in the TOR;

- Confirm the bidder’s agreement that UNIDO shall be entitled to all property rights including but not limited to patents, copyrights and trademarks, with regard to material, and any and all software developed and/or procured externally, whether off-the-shelf and/or proprietary, including libraries and other kinds of software which bears a direct relation to, or results from the services provided to UNIDO by the bidder, if contracted, and that the Contractor shall take all necessary steps, prepare and process all necessary documents and assist in securing such property rights and transferring them to UNIDO for any software procured and/or developed as a result of services prior to transfer of the final payment.

- Reporting

The sub-contractor team will work under the direct supervision of UNIDO

There will be regular and frequent communication to discuss progress and outstanding issues (when required through teleconferencing).

All written material submitted to UNIDO should be in English and of such quality that no additional technical editing is required.

- Proposed Schedule of payments

The proposed schedule of payments is linked to the satisfactory completion and acceptance of deliverables, as shown below.

|  | USD |
| --- | --- |
| 1. Upon signature of contract. (20%) ………………………………………………………… |  |
| 2. Upon satisfactory completion and acceptance of deliverable 1-4, Web site for the NIRP, hosted and maintained. (20%) …….………………………………………… |  |
| 3. Upon satisfactory completion and acceptance of deliverable 5-10, the data collection system plus the database system that stores the collected data and allows query generation. (30%) …………………………………………………………………. 4. Upon satisfactory completion and acceptance of deliverable 10-14, the full package with the data visualization system. (20%) ……………………………………. 5. Upon satisfactory completion of the full system (10%)………….. |  |
| Total |  |

Cost of annual contract for hosting and services in USD: ………………………

Cost Breakdown Table

| Project “Capacity Strengthening for Sustainable Industrial Development in Nigeria-140070” |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Module | Description | Name of Proposer’s staff to be deployed (Provide by job title: developer, tester, trainer, etc.) |  | Total duration (in work-weeks) | Unit cost per work-week (USD) | Total cost (USD) |
| 1 | Operational version of web-site (ver. 1) up and running: | Fill in names below |  |  |  | Sub total |
| 1.1. | Design and mock-up for approval |  |  |  |  |  |
| 1.2 | Beta version and testing |  |  |  |  |  |
| 1.3 | Final version with real data and trained administrators |  |  |  |  |  |
| 2 | On-line data collection system and database designed for efficient query generation | Fill in names below |  |  |  | Sub total |
| 2.1 | Data collection system concept |  |  |  |  |  |
| 2.2 | Data collection system beta version |  |  |  |  |  |
| 2.3 | Tested operational version of data collection system |  |  |  |  |  |
| 2.4 | Database design |  |  |  |  |  |
| 2.5 | Query scenarios tested and design finalized |  |  |  |  |  |
| 2.6 | Final version of data base linked to the data collection system |  |  |  |  |  |
| 3 | Data visualization and report generation system | Fill in names below |  |  |  | Sub total |
| 3.1 | Concept developed |  |  |  |  |  |
| 3.2 | System mock-up |  |  |  |  |  |
| 3.4 | Beat version for testing |  |  |  |  |  |
| 3.5 | Operational system fully functional with real data |  |  |  |  |  |
| 4 | Debugging until acceptable limits reached |  |  |  |  | Sub total |
| 5 | System hosting, including security, backups and updates |  |  |  |  | Sub total |
|  | Grand total |  |  |  |  | Grand total |