## Valuation
KUAJIENA LABORATORY
Item | Description | Quantity | Unit | Unit rate(USD) | Total (USD)
RENOVATIONS OF KUAJIENA TB LABORATORY
B | RENOVATION WORKS
B.1 | Remove existing tiles and screed | 12 | m²
B.2 | Apply 40mm thick cement-sand screed, motar mix 1:3 on cement slurry for proper bonding. | 12 | m²
B.3 | Erect 600mm wideX 900mm high worktop,the slab to the worktop must be reinforced with T12 bars spaced at 200c/c and concrete class C25/20Agg | 1 | item
B.4 | supply and install dobby sinks, works include pipe works and any other works that make the sinks usable. | 1 | item
B.5 | Supply and install 300X300mm ceramic tiles to the floor and on worktop, price include all things like grout, tile adhesives, spacers etc | 20 | m²
B.6 | Supply and fix gypsum plaster board or equally approved acoustic false ceiling panels on steel/aluminum branderings as per site engineers approval. | 12 | m²
B.7 | Allow for the removal of existing window and door | 1 | item
B.8 | Fabricate and install 1500 wide X1500mm high metallic window with 400mm high louvre,two openable glazed leaves and a middle fixlight. | 1 | No.
B.9 | Fabricate and install 1000 wide X2500mm high metallic door, panelled with 3mm thick plate on the downer side and glazed on the upper third | 1 | No.
B.10 | Allow the Provisional Sum for the Construction & completion of sump below the ground level including excavations and disposal all as per Drawings | 1 | item
B.11 | Allow the P.C Sum for the Supply & installation of Water supply pump set, one duty & one stand by capacity 2 kw including valves & pipes as manufactured in either Denmark, UK, USA , Japan or approved by the Engineer. | 1 | item
B.12 | Allow the P.C Sum for the Supply & installation of Solar power system consisting of 8 No. 120W,12A Panels, and all other accessories to complete the installations as manufactured in either Denmark, UK, USA , Japan or approved by the Engineer. | 1 | item
B.13 | Provide, assemble and fix a steel water tower of height 3.85m, and other dimensions and details as shown on the plan for the same. It comprises excavation, reinforced concrete works, structural steels: 100*100*4mm SHS as main component, 50*50*3mm angle bars as ties and struts, 40*40*3mm SHS for the platform and rails, grade 4.6 18mm dia. bolts, 200*200*12mm base plates and 8mm thick gussets at joints of size as indicated on the drawing. Please refer the plan made for the tower and attached here with to compute each activities and materials required for the work. | 1 | item
B.14 | Supplying and installation of 5,000 liters capacity PVC UV protected & anti microbiological protection plastic shell water tank on top of steel water tower structure (Steel structure measured separately ); including a maximum of 120m long 50mm/63mm diameter supply pipe with valve and over flow pipes; complete with other necessary tank accessories for connection to the main building | 1 | No.
B.15 | Allow sum for connecting water to the main supply source. | 1 | item
B.16 | Prepare and apply one coat of primer and two coats of vinly silk paint of approved colour and quality to internal faces of walls | 40 | m²
B | Excavation and Earth Works |  | To Summary
5% contigency
Total
Note on G79: Julious Yuga: The Total figure for this item C proposed by the bidder is : USD 49348.40
Note on G179: Julious Yuga: the Bidder proposed a total price for this G.5 of : USD 1920
Note on G182: Julious Yuga: the total figure for this line, proposed by the Bidder is wrongly estimated at: USD 9,975.00
Note on G265: Julious Yuga: The total price proposed for this item by the bidder is USD 300
Note on G269: Julious Yuga: Total value for H proposed by the bidder in his BoQ is : USD 10820.00
Note on G432: Julious Yuga: The bidder proposed a total price for this item L of : USD 12,195.00
Note on G473: Julious Yuga: the bidder wrongly proposed a total of USD 90 for this item
Note on G487: Julious Yuga: The bidder wrongly indicated a total price of USD 31,500.00
Note on G493: Julious Yuga: The total value for this item M offered by the Bidder is: USD 36,250

## Check List (hidden)
UNOPS - United Nations Office for Project Services
Bill of Quantities
Project: Gintota Secondary School - Galle
Ministry of Education - Government of Sri Lanka
Design Office Estimate
Notes
Generally
(See notes under Preliminaries)
Conditions of Contrcat
The contractor shall price hereunder any obligations contained in the Conditions of Contract which are not allowed for elsewhere and which the Contractor wishes to price separately.
Definitions & Inspection
Engineers & Engineer's representative
Assignment & subletting
Contract Documents
Drawings & Specifications
Obligations of the contractor
Fee issue items
Bonds
Advance Payment
The Site
Contractor's Employees
Plant, Workmanship & Contractor's equipment
Title, risk, care, indemnities and Insurance
Applicable laws
patent & other protected rights
Secrecy
traffic & loads
Commencement & progress
Suspension of Work
Time for completion & Liquidated Damages
Tests on Completion
Taking Over
Defects
Variations
Provisional Sums
Claims
Nominated Subcontractors
Measurement
Extended Warranties from Subcontractors
Intertim & Final Certificates
Payment
Fixed Price
Frustration & Force Majeure
Default of Contractor
Termination for Convenience & Default of Employer
Jurisdiction
Notices
Municipality Payments & Certificates
Restrictions
Access for & possession or use of the site
Limitations of Working hours
Limitations of working Space
Maintenance of existing services on, under or over the site
Execution of the works in sections
Contractor's Administrative Arrangements
Site Administration
Supervision
Security
Safety, Health & welfare of work people.
Trasnsport of work people.
Constructional Plant
Small plant & tools
Scaffolding
Cranes & Lifting plant
Transport
Other plant not listed above but necessary for the completion of the works
Employer's and Consultant's Facilities
Site photographs
Employer's and Consultant's Accommodation
Contractor's Facilities
Offices, Laboratories, compounds, stores, messing facilities and living accommodation
Temporary fencing hordings screens and guardrails
Temporary roads, hardstandings and crossings
Water for the Works
Lighting & Power for the Works
Temporary telephones, telex & facsimile
Temporary Work
Traffic diversion
Access roads
Bridges
Pumping
De-watering
Sundry Items
Testing of Materials
Testing of the Works
Protecting the work from inclement weather
Project Notice Board
Removing rubbish, protective casings & coverings & cleaning the works at completion
Traffic regulations
Maintenance of Public & Privatre roads
Drying the Works
Control of noice & pollution
Statutory Obligations
Quality Control Room
All mock ups, prototypes and samples required by Specification, the Drawings and Schedule of Project Requirements