## Slide 1: Terms of Reference
Qualitative and Quantitative Assessment of Residential Care Facilities in Myanmar

## Slide 2: Background
Increased number of children being sent to institutions – leading to growth of institutional care and orphanages
There is no formal, family-based alternative care system in Myanmar – such as supported kinship and regulated foster care; adoption is rarely practiced
As of April 2018, approximately 21,551 children live in registered institutions – this does not include unregistered institutions
When including unregistered orphanages and monastic care facilities the number reaches over 250,000
Absence of family based alternative care options: supported kinship care and regulated foster care system not yet exist, adoption is rarely practiced and not well regulated
Lack of family support at community levels ->at risk families facing disfunctioning and unnecessary separation/break-down
Orphanages/residential care facilities become a preferred option used as a safety net for children
Institutions/ residential facilities = private, faith-based and monastics institutions/ facilities
244 residential care facilities are registered with DSW and 377 are still unregistered
No accurate data on number of children, exact locations of those unregistered, conditions, situation of children – assessment conducted in 2010-11 covering 147 facilities
Lack of national representative data on the numbers of existing facilities (registered and unregistered, religious based, private based, etc.)

## Slide 3: Why an assessment is needed?
UN CRC Concluding Observations 2012 highlighted the concern about “the increase in the number of children in residential care facilities; the lack of regulation of private and religious organisations that run residential institutions for children; and reports of physical abuse of children in residential institutions” and advised the GoM to address urgently the issue of children deprived of family environment
Increased knowledge and data will inform the Government in decision making and develop proper steps to address the issue
A small scale assessment in 2010/2011 showed high concerns about the living conditions, protection and safety of children in the institutions
There is a high need to improve DSW’s monitoring capacity of all residential care facilities and ensure their compliance to the Minimum Standards of Care and Protection

## Slide 4: Objectives
To conduct the quantitative and qualitative analysis of the situation of children in all residential care facilities in Myanmar.
  To collect qualitative and quantitative information of the situation of children in residential care facilities;
  To develop a comprehensive and standardized tool that can be adopted by MSWRR and other line ministries for routine assessment of child care facilities;
  To build capacity of DSW social welfare officers in routine monitoring and assessment of the residential care facilities with the developed tools;
  To assess the gatekeeping, admission, care plan and reintegration process employed by each facility;
  To identify clear benchmarks and recommendation for each child care facility;
  To provide strategic recommendations to the Government on next step;
  To provide evidence to advocate for more support services for children to remain with families, promote family based alternative care and that institutional care is used as the last resort.

## Slide 5: Expected deliverables
Inception Report with concrete assessment plan;
Final Assessment Tool and Training Module;
Child friendly questionnaire ( ensure to include child protection components)
Conduct training for data collectors/ enumerators
Interim report
Final Assessment Report with strategic recommendations.

## Slide 6: Process
Duration: 5 months (October 2018 – February 2019)
Phase 1: Preparedness
  Establish a Steering Committee led by DSW with representatives from line ministries to oversight the whole process of the assessment and to ensure the implementation of the recommendations as the way forwards;
  Recruitment of the consultancy institution and an international expert to join up as one team to conduct the assessment;
  DSW to identify key staff/social work that can participate in the field assessment team along with the consultants.
Phase 2: Warm-up/Testing
  Inception report with clear conceptual framework developed for undertaking the assignment, methodology, measures, sample assessment tools;
  Implementation plan with timeline and geographical allocations;
  Test the assessment tool, child friendly questionnaires, trainings for members (DSW staff) of the assessment team/data collectors.

## Slide 7: Process (cont.)
Phase 3: Assessment
  Upper Myanmar;
  Lower Myanmar.
Phase 4: Finalisation
  Report write-up and feedbacks;
  Validation of findings;
  Official launch of the assessment.
Phase 5: Way forwards
  National Response Plan developed and adopted;
  Routine monitoring plan developed and adopted by DSW.

## Slide 8: Modality
DSW will lead the whole process - including the recruitment of the consultancy institution, identify key resource DSW staff to join the field assessment team from each State/ Region as well as from Nay Pyi Taw – who will then become the core resource people to conduct routine assessment and/or provide monitoring trainings to other DSW staff;
UNICEF to provide technical and financial support, including the recruitment of an international expert to join up as a team with the national consultancy institution;
ToR of both international and national expert will be developed and shared with UNICEF for inputs
Steering Committee to act as monitoring and quality assurance body.

## Slide 9: International consultant
Designing and developing the research protocol
Designing and planning the assessment process
Developing the assessment/ monitoring tool package and respective training module
Conduct orientation to members of the assessment teams on the assessment/ monitoring tool package
Accountable for overall quality of data generation and analysis
Final deliverable – final assessment report including executive summary, policy brief, power point presentations

## Slide 10: National consultant
Conduct ToT for DSW staff and data collectors/ enumerators involving in the data collection exercise
Facilitate the communication and coordination with local authorities and respective government departments at all levels
Together with international expert, responsible of the quality of data collection and analysis as write up of the final report in Myanmar language
Lead the assessment teams and join the field visits where possible

## Slide 11: Stakeholders
Ministry of Social Welfare, Relief and Resettlement
Ministry of Border Affairs
Ministry of Religious Affairs
Ministry of Health and Sports
Ministry of Education
Ministry of Population and Immigration
Central Statistics Office
NGOs, Faith based organiations, Community based organisations
Residential care facilities
UNICEF

## Slide 12: Thank You!