|  |  |
| --- | --- |
|  | **CONSULTANCY /STC** |

**SCHEDULE OF ACTIVITIES FOR THE 30 DAYS CONSULTANCY**

| **Activity** | **Deliverables** | **Duration** |
| --- | --- | --- |
| 1. Organize a TC with WHO/CLO-FSM, WHO DPS and MoH and Desk review of the country situation and IHR-related areas | * 1. Country visit agenda draft | 2 day |
| 1. In collaboration with the MOH, airport and seaport authorities, complete the detailed spreadsheet on IHR capacities at points of entry | * 1. Completed PoE assessment for air and sea ports | 25 days |
| 1. Conduct JEE data collection, draft self-assessment report and National Health Security Action Plan | * 1. Stakeholders mapped and included in the country debrief and mission report   2. Internal assessment report drafted with the score sheet filled up and the repository created with the documents uploaded   3. National Health Security Action Plan drafted |
| 1. Support the development of slides for the external JEE | * 1. 19 slides sets developed   2. Practice sessions conducted |
| 1. Brief health leadership and partner agencies on the JEE internal assessment process and provide a debrief at end of mission | * 1. Note for the record of both meetings | 1 day |
| 1. Provide WHO with a mission report within one week of departure | * 1. Finalised mission reported | 2 days |
| **Total days Full Time Equivalent (FTE)** | | **30 days** |